## Summary
MANA Training / Go-Live Issue Tracker
Consolidated log of items raised to Ruben and Andy across training sessions
Tab | Description | # of Items | Overall Status
Ops Sessions - Open Items | Eligibility, Front Desk, Scheduling, Technologists, Billing session findings | 5 | Mixed - 1 Resolved, rest Open (updated 8/10)
Coding & Admin - Open Items | Coding and Admin training session findings | 7 | Mixed - 2 Resolved, rest In Progress/Open (updated 8/10)
Q&A Log - Answered | Front Desk, Scheduling, Technologists, Pre-Auth, Foreign Films Q&A with answers received | 14 | Mixed - see Status column (updated 8/10)
Legend:
Open / Needs Action
Pending / In Progress
Resolved / Confirmed

## Ops Sessions - Open Items
Ops Sessions - Open Items
Eligibility, Front Desk, Scheduling, Technologists, and Billing sessions - items for Ruben and Andy
# | Category / Session | Issue Summary | Details | Action Requested | Status
1 | Scheduling / Front Desk / Technologists | Scheduling wizard defaulting to wrong location | When scheduling from a pending appointment that came over from ECW, First Available keeps defaulting to "Scheduling" instead of the correct center (Mana Imaging or Pinnacle depending on the patient). Occurred in Front Desk, Scheduling, and Technologists sessions today, including on a patient that scheduled correctly yesterday - appears intermittent rather than a one-off. | 8/13 Update: Dawn will also submit an order from eCW to continue testing 8/13 Update: Determined that Kayla Caler and Ruben A-Scheduling in wizard, which is incorrect. We should be seeing what dawn sees with Mana Imaging and Pinnacle location. Ruben and Andy to investigate | In Progress - Needs Investigation
2 | Front Desk | Manual scheduling not carrying over the procedure | In the Front Desk session, the manual scheduling calendar view was not pulling the procedure over to drag onto a time slot (tested by both Dawn and reporter). Worked fine in the later Scheduling session - may be related to Item 1. | 8/13 Yes, this is related to item 1 Ruben and Andy to investigate; possibly linked to Item 1 | In Progress - Needs Investigation
3 | Eligibility / Billing | ECW walk-in X-ray order landing with "pending authorization" reason | An X-ray order that came over from ECW showed a pending reason of "pending authorization," even though walk-in X-rays do not require auth. | 8/13 Update" Follow with Rafael A. Confirm what is driving the pending reason for X-ray orders from ECW | In Progress - Needs Confirmation
4 | Scheduling | Pinnacle visibility needs to be conditional, not a blanket hide | Follow-up on earlier ask to hide Pinnacle Hills from FTC schedulers. Brice, who books his own X-rays and is based at Pinnacle, still needs Pinnacle as an option. Needs to be set per user/role rather than hidden network-wide. 8/10 Update: Ruben created a new "Pinnacle Hills" region containing only the Pinnacle Hills location and reassigned Bryce Smith to it (previously under the broader "Mana Imaging" region), so he now sees only Pinnacle Hills. Confirmed Mana Imaging-region staff do not see Pinnacle Hills. Also removed an over-broad "Mana MRI" location from Ramanda Snow's access, leaving her with Mana Imaging only. Follow-up: confirm remaining Pinnacle Hills staff (e.g., Michelle) are built into the system - Craig is cross-checking Active Directory; 3 newly added AD group members still need to sync/map on the AbbaDox side; add clearer descriptions to existing regions without renaming them since they're already assigned; double-check Hog Mountain Home region assignment as well. | Confirm remaining Pinnacle Hills staff are mapped; complete AD sync for 3 new users; add region descriptions | Resolved - Region Created (AD Sync Follow-up Pending)
5 | Technologists / Admin | Edit Tech Complete permission grayed out for admin user | Admin user (Dawn) had the Edit TechComplete option grayed out yesterday when trying to correct a contrast entry, even though it should be available to anyone with admin rights. Maggie offered to check role settings. | Confirm what Maggie finds in role settings | Pending - Awaiting Maggie's Review

## Coding & Admin - Open Items
Coding & Admin - Open Items
Coding and Admin training sessions with MANA - items for Ruben (MANA team to confirm/add as needed)
# | Topic | Issue Summary | Details | Action Requested | Status | Ticket | Ticket | Ticket
1 | Custom Reports (Tyler) | Requested custom reports not found in Analytics | Dawn/team asked Tyler to build custom reports a while back and can't find them in Analytics. Unclear if they were finished, named differently, or not shared with her permissions. 8/10 Update: Still unresolved. Ruben to confirm with Josh and Paul on request status and report names, then reply directly to Dawn's email so the team knows what to search for. | 8/13 Determined that Automated Monthly Reports looks in progress in Jira. Check with Tyler/Josh/Paul on status; reply to Dawn's email with report names | In Progress - Ruben Confirming with Josh/Paul | https://pinkypixels.atlassian.net/browse/AN-1977 | https://pinkypixels.atlassian.net/browse/AN-2004 | https://pinkypixels.atlassian.net/browse/AN-2016
2 | Report + Manage Procedures Side-by-Side | Coders need report and procedure editing visible simultaneously | Coders need to view the report and edit modifiers/diagnosis at the same time instead of switching screens. Dawn mentioned a "Coding New" tab in progress at one point meant to solve this. 8/10 Update: A true side-by-side/pop-out view is likely not available. However, the worklist has been updated with a View Report (VORX) button so coders can view the report within the pane without navigating to the patient chart. Ruben to confirm internally whether a true pop-out from the pane view is possible. | Confirm with team whether pop-out from pane view is possible | Partially Resolved - View Report Button Added
3 | Contrast Toggle in Local Procedures | Contrast toggle missing on at least one procedure | Need to verify all of MANA's contrast procedures have the Contrast toggle turned on so the Contrast widget shows up in Tech Workflow. At least one test procedure found missing it. | Confirm who owns checking/fixing this | Open - Needs Owner
4 | Revising Report Body Without Addendum | No workflow to correct finalized report body without formal addendum | Admin needs a way to correct errors in the body of a finalized report (wrong procedure, modifier, or contrast description) without requiring the radiologist to do a formal addendum. Comes up often enough to be a real workflow gap. 8/10 Update: Ruben demonstrated the full workflow live: (1) Procedure-only correction - open the patient chart, go to the appointment, use Manage Procedures to change the procedure, then take the accession number to the Waffle Menu > Order Finalize > reprocess so the report reflects the corrected procedure (note: this does not itself flag that a manual revision occurred). (2) Report body text correction - requires a specific role granting access to the "Order Lookup" tool; from there, locate the order, select Reopen, edit the report body text, and Save. This role is not yet assigned to Dawn's team - needs to be configured via Settings > User Role Assignment > Role Definitions. Once access is granted, the team will need a guided walkthrough. | Grant Order Lookup role access to Dawn's team; schedule follow-up walkthrough | In Progress - Workflow Demonstrated; Role Access Pending
5 | Unread Studies Report | Confirm correct report for unread/undictated exams | Lynette found this report and it appears to cover exams without a finalized/dictated report. 8/10 Update: Lynette confirmed this is the custom report requested from Tyler. Still waiting on the same confirmation as Item 1 (report name/how to locate it). | Confirm this is the right report and there isn't a better option; tie resolution to Item 1 | Open - Tied to Item 1 (Custom Reports)
6 | Pending Studies Worklist | Only Dawn can pull data into worklist | Dawn is the only one who can pull data into this worklist. Craig, Brittney, and reporter all tested with the same date range and got nothing. 8/10 Update: Root cause identified - the Administrator role already includes "Pending" under Workflow Access (the separate CareFlow Admin role does not, but that's fine since affected users have Administrator). Also removed the unrelated "Reporting" workflow item from Dawn's access during the call, since that view is for a transcription/radiologist-review workflow the team doesn't use. | No further action - confirm other affected users (Craig, Brittney) have Administrator role | Resolved - Administrator Role Confirmed
7 | Appointment Status List / DFT Trigger | Trim unused appointment statuses for coders | Dawn asked to trim the appointment statuses coders click through since several aren't used. Understanding is the list is account-level and can't be altered by role/location, so any change affects everyone. Related to coding-complete vs. billing-complete discussion (billing complete triggers the DFT to ECW) - need alignment on which statuses are needed before changing anything. 8/10 Update: Confirmed trimming statuses is all-or-nothing at the account level (affects Breast Center too) - Dawn to coordinate with Carrie on which statuses to disable via Settings > Statuses. Billing/coding-complete workflow decided: coders will flip most locations directly to Billing Complete; Highland Group (HOG) locations stay at Coding Complete for now and will be manually flipped to Billing Complete by Brittany/Kaylin after insurance review, to be revisited about a week after go-live; Ozark is expected to flow through fine once coders add diagnosis. Outstanding: configuring the DFT message to only send at midnight for specific locations remains open with Ruben's engineering team. | Dawn/Carrie to align on statuses to disable; Ruben's team to finalize per-location midnight DFT trigger | In Progress - Workflow Decided; DFT Config Open with Dev Team

## Q&A Log - Answered
Q&A Log - Answered
Front Desk, Scheduling, Technologists, Pre-Authorizations, Foreign Films - questions raised with answers received
# | Category | Question | Answer / Status Update | Status
1 | Front Desk | When will the fix for the router print formatting issue (line cutting through the procedure field text) be implemented? Ruben mentioned widening the field/cell as the solution. | This has been fixed. (Reconfirmed fixed as of 8/10 call.) | Resolved
2 | Front Desk | Why does Mana MRI never appear as an option when searching the check-in/check-out worklist by location, even with the correct modality selected? | Location visibility has been confirmed on our end. Need more detail on how the list is being displayed/filtered to pinpoint the discrepancy. 8/10 Update: Ruben was able to see Mana MRI in the check-in/checkout location list when testing, so could not reproduce. Suspects Karina's account may have a different/off regionalization setting causing the discrepancy. Needs to reproduce directly with Karina to confirm. | Open - Needs Repro with Karina (Possible Regionalization Issue)
3 | Front Desk | Can Pinnacle Hills be hidden from the front desk/scheduler view so it can't be accidentally selected? (Ruben confirmed possible - Dawn requested it.) | Need to confirm whether the hide should also apply to the Wizard and Calendar views in Check-In, or just the scheduler view. Also need to understand the intended use case for this location going forward. 8/10 Update: Resolved by creating a dedicated "Pinnacle Hills" region containing only that location and reassigning Bryce Smith (based there) to it, so he now sees only Pinnacle Hills instead of the broader Mana Imaging region. Confirmed Mana Imaging staff do not see Pinnacle Hills. Follow-up: confirm remaining Pinnacle Hills staff (e.g., Michelle) are built into the system - Craig is cross-checking Active Directory; 3 newly added AD group members still need to sync/map on the AbbaDox side. | Resolved - Region Created (AD Sync Follow-up Pending)
4 | Front Desk | Does correcting an order in ECW (e.g., changing a 2-view X-ray to a 3-view) automatically sync that update to CareFlow? Ruben said he'd confirm via the SIU interface. | Yes - this update flows through automatically via the outbound SIU interface. | Resolved
5 | Scheduling | If the referring physician on an in-network order is incorrect, can staff correct it directly in CareFlow, or would that break report-matching back to the ECW order? | Ruben is not yet certain of the full impact; the outbound SIU interface should cover this but needs to be verified. Will advise with MANA on testing this scenario and deciding the best path forward. | Pending - Testing Needed
6 | Scheduling | Is there a comment type that will actually print on the router, so techs are alerted to hold a stat walk-in for a callback? | Discussed adding a procedure note field for this purpose. AbbaDox is in the process of adding this field within Reforma. 8/10 Update: Ruben to follow up with Madeline - she previously requested this field be made available in Reforma so it can be mapped into the appointment notes under chief complaint. | Pending - Ruben Following Up with Madeline
7 | Scheduling | Why did an X-ray order that Dawn canceled in ECW remain in the CareFlow pending list instead of clearing or showing as canceled? What is the expected/correct behavior? | Requires confirmation from the interoperability team on both AbbaDox and eCW sides to determine correct expected behavior. Need a sample case (patient, order, timestamp) to trace through the interface. 8/10 Update: Investigated via the HL7 viewer - messages that ECW reports as sent with a Cancel (CA) status code appear to be coming across to AbbaDox mapped as New (NW) instead, suggesting a mapping gap rather than a missed message. Reoccurred today (8/10) when Dawn canceled another order in ECW and it again did not flow through. Ruben sent a sample order to Nahil and Rafael on the dev team to investigate and fix the mapping. | Open - Mapping Issue Identified, Sent to Dev Team (Nahil/Rafael)
8 | Technologists | Why does changing or adding a procedure from Appointment Details (Manage Procedures) force a full reschedule and fail to hold the existing time block, when doing the same change from the Tech Complete tab does not? | Depends on whether the new procedure is within the same service type. Same service type: CareFlow should not trigger the Wizard. Different service type: Wizard will prompt the user to drop the procedure into the Calendar for scheduling. | Resolved - Documentation Update Needed
9 | Pre-Authorizations | Can a dedicated role scoped to Eligibility and Pre-Auth (plus patient search, patient chart, and tasks) be built and assigned for Lynette's team, instead of their current broader scheduler/registration role? | Yes, this can be accomplished through the Roles Assignment setting. 8/10 Update: Despite this, Lynette's PreAuth team members can see the PreAuth worklist but nothing populates in it for them. Ruben compared two team members' (Emily and Lynn) role access and found them identical, suggesting the gap may be a filter setting rather than a missing role/permission. Lynette to check with her team on what they're actually seeing and report back. | Open - Investigating Filter/Access Discrepancy
10 | Pre-Authorizations | Is there a lock or indicator for concurrent access on the pre-auth worklist (similar to fax sorting) that flags when a second person opens a record already in use - and if not, can one be added? | Ruben will follow up to confirm whether the functionality currently exists or would need to be added. 8/10 Update: Re-confirmed still needed - concern is two people (including remote staff) working the same pre-auth record at once without knowing. Ruben will check whether a record-lock feature can be added. | Pending - Ruben to Follow Up
11 | Foreign Films | When two foreign film exams are scheduled on the same visit, will they generate two separate claims/accessions in ECW? | Yes. | Resolved
12 | Foreign Films | Can the overbooking issue be fixed where foreign film exams aren't stacking correctly at the intended 8:00 slot when two exams are booked together? | This is expected behavior, not a bug. The workflow intentionally has staff double-book exams at the 8:00 slot so that no other availability displays to schedulers when booking these exam types. | Resolved - Expected Behavior
13 | Foreign Films | What is the actual purpose of the "Foreign Films" pending worklist, given that scheduled foreign film/dictated letter appointments (status "new," not "pending") don't appear there - and is it usable for checking add-ons? | This worklist can be removed if it's not currently serving a need. Original purpose was to serve as an extra reference tool for Brittney when creating orders while cross-referencing OneEMR. | Resolved - Candidate for Removal
14 | Foreign Films | Since foreign film/dictated letter appointments don't generate an ECW claim, what actually triggers the appointment status to mark as complete? (Working theory: PowerScribe flips it once the report is attached.) | Confirmed - the working theory is correct. PowerScribe marks the appointment complete once the report is attached. | Resolved