## Bug Tracker
Assignment | Description | Current Status | Who's Working | Date Submitted | Est. Completion Date
BUG-2723 (PVS-957) | Complex Procedure – One Sub-Procedure Missing Description in Parent Appointment Section After Changing Procedure | 6/23 Pending Deployment to QA 6/10 Rootcause identified and code updated. Development status has Pending Deployment to Delta which is our pre-production site. Fix should be in production next week. 6/9 Defined - Reproduced in RMITest — when changing a procedure to a Complex/Combo type via Manage Procedures, one of the two child procedures under the parent appointment does not display its procedure description after scheduling; issue confirmed persistent as of May 2026." | Done | 2026-01-20 | 2026-06-16
BUG-2808 (PVS-986) | Combo Procedure – Procedure Missing Accession ID After Changing from Complex to Combo via Manage Procedures & Services | 6/23 Requires internal follow up. 6/18 Returned to development, proposed fix did not pass QA. 6/9 In Progress - Root cause identified in patientvisitsummary/EditVisitController.cs — explosion code children created via MPAS procedure change never receive an accession ID due to missing AppointmentItemId and no order creation logic; fix ready for review. | Done | 2026-04-17 | 7/31 BC retested workflow and confirmed solution. 7/24 Bug was not able to reproduce, in other words the application is working as expected. 7/22: Development could not reproduce - Ruben is testing to reopen if neeeded 7/23: unable to reproduce, customer is notified
BUG-2785 | Display minutes since last update | 6/23 Pending Push to Production 6/18 Udpated to QA status 6/9 Being Prioritized | Done | 2026-04-10 | TBD - Tentative timeline 6/26
BUG-2875 | Cancelled procedure persists in scheduling wizard when adding a new procedure to the same visit | 6/23 Pending Push to Production 6/23 6/18 Pending Deployment to QA 6/18 Udpated to QA status 6/9 Being Prioritized | Done | 2026-05-01 | TBD - Tentative timeline 6/26
BUG-2873 | Scheduling Rules Canceling Each Other Out | 6/23 Same status 6/18 Pending Deployment to QA 6/9 Being Prioritized | Done | 2026-05-01 | TBD - Tentative timeline 7/6
BUG-3202 | MANA - Change Complex Template Forces Unnecessary Manual Scheduling Steps for One-to-One Template Swaps | 7/21 Reported on 7/16 while testing. Ticket pending prioritization | In Progress - Not a showstopper (7/24) | 2026-07-24 | 7/24 Because Bug PVS-986 has been fixed, the team confirmed that techs will likely change procedure but ungrouping the complex first, without the need to change template but rather change at procedure level. It was also confirmed that this will be of minimal effect to the schedulers, because its preferred schedulers to do have the option see the schedulers. This is also a cleaner than the current process and is also a simila number of steps to the procress. 7/22: This could be addressed by the change in workflow being built by Inland
BUG-3199 | MANA - Template Change Within a Visit Silently Reassigns Appointment Location | 7/21 Reported on 7/16 while testing. Ticket pending prioritization | Done | 2026-07-24 | 7/31 Fix is now completed and has been pushed to production. 7/24 This will not be an issue because moment in which bug is visible will not be in path of users changing the exam. In this case, technologist will not be pursuing this workflow, and Schedulers will just reschedule from Scheduling manager, not manual scheduling (which is the function that presents the issue) 7/22: Confirmed that this would be considered a bug - assigned S1 priority 7/23: Only ticket needed at this time
Enhancement Card #2135 | Allow single Appointment ID to span multiple modalities (currently splits into separate MagView group entries) | 7/21 Enhacement Card submitted, pending PO Review | In Progress | 2026-07-21 | 7/24 Update to interface logic from Magview will determine if this is still need. 7/23: Will be overcome by Jason and Rafael Aburto.
Enhancement Card #2200 | Auto-refresh page after removing complex grouping (remove manual refresh requirement) | 7/27 Enhacement Card submitted, pending PO Review | In Progress | 2026-07-27 | 7/27 Request submitted for enhancement. Request under review.
Enhancement Card #2280 | Comments Column on Pending Appointments Workflow Should Display Appointment-Specific Comment, Not Patient-Level Comment | 8/11 Enhacement Card submitted, pending PO Review | New | 2026-07-27 | 8/14 Request submitted for enhancement. Request under review.

## Project Tracker
Level | Category | Vendor | Ticket | Topic | Notes | Date | Owner | Status
0 | UAT
2 | UAT | Imaging |  | Billing Workflow |  |  |  | Completed
3 | UAT | Imaging |  |  | 4/8 Confirmed workflow and worklist with Team on 4/2. Upload to Procedure summary report are now available as well. Update to worklist required per conversation on 2/12 | 2026-04-08 |  | Completed
| UAT | IC |  | Workflow
[5 empty] | 8/19 AbbaDox working through list of items with Dawn and Imaging Center 8/11 Contrast selected for contrast proc. 8/6 AbbaDox to enablem Contrast exams in Local procedures to display button in TechComplete 8/6 AbbaDox to follow up on UAMS location availability. 7/31 All rules are built and tested. Marking as completed. 7/22 Build out "dictated letter" Notification slot at all MANA Imaging center and foreing film locations. 7/15 Up to date with all workflow reviews 7/8 Reviewed Order Intakes and Scheduling | 2026-08-19 | AbbaDox | 100%
2 | UAT | BC |  | Workflow
3 | UAT | BC |  |  | 4/1 Billing workflow signed off. The team is currently testing OB DFT with Modifier. This is interface related. Carrie to confirm with Kim sign-off on Billing Workflow, MANA | 2026-04-01 | Carrie / MANA | Completed
[5 empty] | 8/19 Breast center will implement a phased go live - Go live TBD 8/11 BC has been testing application and defined new issues to be reviwed. Go live date dependent on issue definition and next steps. 8/6 Reported that Contrast is not visible in the Visit wintdow, which is what we had determined as window for techs to use. Will review with the team on tomorrow's call. 8/6 BC running additional testing sessions and determine if more updates is needed. AbbaDox confirming that Task automation is enabled. 7/31 Change Complex Procedure workflow has been tested and passed. 7/22 Enhancement submitted to Allow single Appointment ID to span multiple modalities (currently splits into separate MagView group entries). Also, Two new bug tickets submitted. 7/15 Up to date with all workflow reviews - Revising Change Complex Template 7/8 Review Registration with Amber and Billing with Kim. 6/3 Complex Procedure setting tested. 5/13 Amanda confirmed buid of Questionnaire 5/6 Reviewed Questionnaire, Amanda has already made updates. Further review of bugs to reviewed to Friday. 5/6 List sent to AbbaDox, proceed to map Federal payers to G-codes 4/29 Medicare to be automated into the specific procedures. 4/22 During MagView call, an issue was determined when canceling an exam and adding a new one to same visit. Ticket required for follow up. 4/22 Began UAT of Billing Workflow. Bugs have been prioritzed by leadership. 4/15 Road block Changing Procedures, specifically for Complex and Combo procedures. 4/8 Extending Tuesday and Friday to two-hour sessions. 4/8 UAT revamped on 4/7 4/1 MANA and AbbaDox will meet on Tuesdays and Fridays to test workflows. | 2026-08-11 | AbbaDox | In Progress
1 | Training
3 | Training |  |  | Discuss training plan with Tyler on 3/18 |  | 3/11 | Tyler | Completed
[5 empty] | 8/19 Need to determine traning for Breast Center 8/12 Training completed for IC. Pending Breast Center. 8/6 IC training on going, Scheduling training for BC for week of 8/17 7/31 Scheduling training with IC on 8/06 and BC 8/10 - BC to catch up with AbbaDox training team. 7/22 Training paused until new go live date is established. 7/2 Moving to scheduling training with IC on 7/13 and BC 7/20 - Need recap with Tyler. 5/22 - Darron discussed with Ruben, Dawn, and Kim independently about a tentative go-live 3rd week of July with training to take place in the preceeding two weeks. Asked everyone to check schedules and availability (pending bug fixes). 4/15 Training data is TBD depending on bugs fix. 4/8 Training will depend on go live date which depends on BUG fix. 4/1 Training modules, wiki, and calendar to be shared with by Ty. | 2026-07-31 | Tyler and Corinna | In Progress
1 | Interfaces |  | Feature-707
2 | Interfaces | Merge PACS |  | Scope: Uni. ORM, ADT, ORU |  |  |  | Completed
2 | Interfaces | PowerScribe |  | Scope: Bid. ORM, ADT/ORU – Thursday at 12:00 PM EST |  |  |  | 100%
3 | Interfaces | PowerScribe |  |  | 4/8 Client reported ORU transfer takes 7-8 minutes 4/8 AbbaDox receiving ORUs as expected for all locations. Completing task. 4/1 Interface ready for testing the IB ORU 3/27 Proposed Fix: Configure PowerScribe to send the report upon radiologist finalization, bypassing the order completion status requirement. FF Results not processing in AbbaDox if appt. is not in TechComplete status | 2026-04-08 | AbbaDox | Completed
| Interfaces | PowerScribe |  | Contrast Waste | 5/27 Test was succesfull, there's a need to determine where in Rad templates need the contrast waste include. 5/6 MANA working on updating PS360 to process OBR.20 and capture Contrast waste in the report. 4/29 Meeting scheduled with PS360 to discuss update. Include Procedure Note in Technologist window to send downstream to PowerScribe for Waste, OBR.20. 4/22 This is a PS360 Issue where dictation appears to be capturing the Contrast sent by AbbaDox. | 2026-04-29 | MANA | Completed
2 | Interfaces | MagView |  | Scope: Bid. ORM, ADT/ORU – Tuesdays at 12:00 PM EST |  |  |  | 90%
3 | Interfaces | MagView |  |  | 8/11 Testing has progressed, Jason updates were positive. team will continue testing in AbbaDox and test interface. 8/6 MagView made additional updates, MagView appears to be grouping and separting procedures. Jason will continue to make additional changes. Meeting again on 8/7 7/31 Carrie confirmed Appointment ID grouping logic in Magview is working. Team testing ungrouping logic, stand-alone. Outstanding question around grouped vs Standalone. 7/22 Successfull on sending grouped Appointment ID when updated with in AbbaDox. Carrie and Amanda will do further testing. 7/15 Jason unable to remote to Magivew's environment, reschedule to today for further Troubleshooting. 7/8 Abus interface message being fixed by Magview. 7/8 Issue with combo code found and fixed after call. 7/2 Interface is ready for go live, Carrie will continue to test interface accordingly. 6/26 Same update. 6/10 Complex procedures can't use the standard AB26 visit ID since grouped exams have differing visit IDs, so MRN + date of service is used instead — but this breaks on reschedules, leaving orphaned records; Jason is exploring using persistent procedure accession numbers as a fix. 6/3 Pending on Jason's return to discuss exams migration with Paul. 5/27 Carrie to further testing - mainly on changing procedures. 5/13 MV made a few modification to visit ID. 5/6 MV corrected procedures not displaying exams. Carrie will continue to test. Amanda will assist Ruben on reproducing bug of canceling and adding new procedure under same visit. 4/29 Jason made updates to the interface. Carrie will proceed to test prior to next next meeting. 4/29 Naheel confirmed modifications to transmit the patient DOS and parent procedure for PV1.19. Team addressed data issue where DOB was incorrectly populating instead of DOS. Next steps- preliminary email testing and a full round of testing at the next meeting, pending on Jason changes and Carrie generating new messages for both testing scenarios. 4/22 Team following up with Magview on Friday. 4/22 Encountered issue with Magview sending back ORU for Combo procedure. Determined workflow for updating exam of different service types. 4/15 Adjustments required to ORM, stakeholders meeting on 4/17 to continue. 4/8 Testing is on going after additional updates to complex procedures config. 4/1 Carrie testing all procedures sent downstream. Interface testing with all procedures | 2026-07-31 | MANA | In Progress
2 | Interfaces | eCW |  | Scope: Bid. ORU, ADT, DFT, SIU/ORM, ADT (Alex) – Thursday at 2:00 PM EST | 8/6 Note: Update Henna on 8/11 about go live readiness. Note: eCW Version in test is 12.0.3 |  |  | 100%
3 | Interfaces | eCW |  | Compendium | 4/1 This is a cut-off innitiative, no longer interface related. 3/25 Dawn will extract and review local procedures with Steven. Upon go live, there will be a cutoff initiative to disable the "old" merge procedures so that users don't order these via the int. Compendium updated, to be shared with eCW. | 2026-04-01 | MANA | Completed
3 | Interfaces | eCW |  | Foreign Films | 3/26 Confirmed that foreing films are being excluded in SIU interface 3/25 AbbaDox updated the GLV, pending on update to the inter. It appears is not yet filtering accordingly. | 3/18 | MANA | Completed
3 | Interfaces | eCW |  | Referring Practice NPI | 3/25 Steven will confirm that this is completed. | 2/4 | Steven | Completed
3 | Interfaces | eCW |  | Testing | 3/26 Confirmen that DFT was received in eCW 3/25 Test OB DFT interface. Test in Imaging and Breast Center Appointment. | 2026-03-25 | MANA | Completed
3 | Interfaces | eCW |  | Resource Mapping | 3/25 Resource and Rooms download includes External Resource ID. MANA will revise entries in external resource ID in AbbaDox. | 3/18 | AbbaDox | Completed
3 | Interfaces | eCW |  | OB DFT | 7/2 Interface testing Completed, ready for an end to end session. Alex and Darron will assist on advising eCW accordingly. 6/26 Provide notice of two week of golive date prior to interface cutover. 6/3 Pending update to GLV for further testing. 5/27 Follow up Steven's email from test with Brittany, it appears so DFT may not be processing for -26 5/22 Billing provider was added, DFT appear to be crossing as expected 5/13 Determined that IB DFT to eCW failed because of Billing Provider. 5/13 Began testing updates to DFT message to include Modifier during specific scenarios. 5/6 Logic to send 26 modifier has been update with GLV. Ready for testing 4/8 OB DFT Message tested on 4/1. AbbaDox to apply additional update to Foreign Films Modifier logic and Dummy Diagnosis. 4/1 MANA testing OB DFT to include Modified | 2026-07-02 | AbbaDox | Completed | MANA - Interface_Testing_Scripts.xlsx
3 | Interfaces | eCW |  | Duplication of Report | 4/8 Plain text OBR rather that embeded PDF. | 2026-04-08 | AbbaDox | Completed
3 | Interfaces | eCW |  | Facility ID update | 4/8 IC - Steven will be providing new Facility ID for AbbaDox to update the Foreign film location | 2026-04-08 | Steven | Completed
3 | Interfaces | eCW |  | Compendium update | 4/22 This has been completed 4/15 Need to update exam code by removing space between dash. Requirement by eCW | 2026-04-22 | AbbaDox | Completed
3 | Interfaces | eCW | DS-1468 | Mapping of modifier | 6/26 Locations added, need to add procedures. 6/10 AbbaDox to include Highlangs and Ozarks to logic accordingly. AbbaDox also added more procedures to the list, but after validation it appears a few are still missing. AbbaDox also update GLV to 6/3 Team updated list in Sharepoint, AbbaDox to GLV 6/3 Brittany helping provide additional procedures to be added to GLV. Ruben updating the Local procedures with Modifiers. 5/27 One last GLV to be updated that's is blocking last insterface script. 5/22 Mapping is completed but GLV needs to be reviewed. 5/13 AbbaDox updating GLV to include more procedcures in OB DFT logic. 5/6 AbbaDox to include procedure to dummy diagnosis GLV. 4/29 Generic List of Values updated, pending on configuration and testing. 4/22 List of procedures are being uploaded to finalize interface logic 4/15 Abbadox working on update to interface | 2026-06-25 | AbbaDox | Complete
3 | Interfaces | eCW |  | Provider | 5/27 This is completed 5/13 Selection provider in AbbaDox has been succesfull to eCW. Will keep in progress as the team confirm other providers in message do no get excluded. 5/6 Confirmed that PV1 includes provider, Carrie is testing. 4/29 eCW received indications where providers are being sent from AbbaDox. 4/22 Need to reasses issue with Payer and Referring provider being sent in interface to eCW | 2026-05-13 | MANA | Completed
3 | Interfaces | eCW |  | Payer | 7/8 Payer have been cleaned up 7/2 DS-1546 - Ticket for payer clean up 6/26 Clean up of Payer required. 6/10 It appears that AbbaDox payer Client Code of "100000" is not one that exist in eCW. eCW hosts a four digit code instead. Consider the need to clean up Payers list in AbbaDox. This does not break eCW as eCW has a mechanism to look at insurance in eCW patient record. 5/27 Need to confirm that payers are being transmitted. 5/22 Claims appear to be processing in eCW - This Task may be completed. 5/13 Until we accomplish a succesfull claim while test the OB DFT to eCW, this is on hold. 5/6 Brittney will continue to test payer assigment in AbbaDox, that is then sent OB to eCW. | 2026-07-02 | AbbaDox | Completed
3 | Interfaces | eCW |  | Compendium | 5/6 Compendium has been accepted by eCW. Ready for testing. 4/29 AbbaDox compendium has shared list of procedures to eCW. Need follow up to eCW. | 2026-04-29 | eCW | Completed
3 | Interfaces | eCW |  | iConnect | 5/27 Tested and confirm this is good. 5/13 To be discussed with AbbaDox. 5/6 interface workflow has to be defined, it appears that the Iconnect link in ORU may be passed through AbbaDox to eCW. | 2026-05-13 | MANA | Completed
|  |  |  | Authorization in 2nd Payer | 7/15 Determined with eCW mapping second auth is an enhancement. Will not be ready for go live. 7/15 Discovered on 7/14 that Auth in Secondary insurance is not being mapped in eCW to expected field. |  |  | Completed
3 | Interfaces | eCW |  | Locations | 7/15 Removed duplicate - BFDC, confirm workflow change. 7/8 When ever Karas is used as location, the location code must be updated to BFDC. 6/10 There's an existing location mapping between Merge and Ecw that AbbaDox must immitate. When Karas location, transmit the BFDC instead Karas code. | 2026-07-15 | AbbaDox | Completed
2 | Interfaces | Outreads Flatiron / OncoEMR HOG | IN-2862 |  | 7/8 Brittney tested the interface and advised HOG of go live on 7/28 7/2 Brittney will assis on advising Flatiron of the go live date of 7/28 6/3 Update Flatiron of the penciled go live date. 4/15 AbbaDox to advise Flatiron on decided go live date. |  |  | 100%
3 | Interfaces | Outreads Flatiron / OncoEMR HOG |  | sFTP | 4/8 Flatiron ready for go live. Need to provide go live date. 4/1 Interface has been updated and ready for testing 3/25 AbbaDox to include FF rooms in this interface. Rooms have been confirmed and in ticket request. AbbaDox dropping messages in the sFTP. | 2026-04-08 | AbbaDox | Completed
2 | Interfaces | Hologic | IN-3335 |  |  |  |  | 100%
3 | Interfaces | Hologic |  | Testing | 7/2 Carrie tested interface after Hologic secure exhange update, all look good, another testing happening on the 7/10 6/18 June 18th is the target for the installation of new the Secure Exchange Router 5/27 MANA waiting on new router. 5/13 MANA reviewing update to router/Candelas/Secure Exchange. Craig in the meantime in share request to Ilana via email. 5/6 AbbaDox made an update to the inteface to cancel and send new order. It appears that Candelas does not accept the new order while having the same accession. MANA will revisit quote with Candelas to update router. 4/29 AbbaDox to apply update. 4/29 Hologic requires rescheduled studies to trigger a new Accession ID, and while AbbaDox's proposed fix is to generate a new Accession ID/Visit ID on reschedule, Craig notes the Candelas box's ability to handle requires testing to validate the solution. 4/22 MANA pending on update from Candelis. 4/22 Met with Hologic on 4/17. Interface is enabled, need to confirm next step. 4/15 Met with hologic on 4/10, update from Hologic is still required 3/27 Confirmed with Hologic that accession does not need to update in AbbaDox. Hologic needs to provide feeback from Candelis on the update of DOS when rescheduling. Carrie: This is a show-stopper for Go Live, but not a training show-stopper. 3/25 Reschedule must change the accession in AbbaDox. AbbaDox to determine if accession can be updated. MANA. Hologic interface appears to be enabled, testing is ongoing. | 2026-07-02 | Hologic | Completed
1 | Data Migration |  | DS-696
2 | Data Migration |  |  | MANA assisting on Merging patients |  | 2/11 | MANA | Completed
3 | Data Migration |  |  |  | eCW patients in Merge that require merging. MANA will not merge in eCW, but rather in AbbaDox. MANA will keep list and provide to AbbaDox prior to go live. | 3/4 | MANA
| Data Migration |  |  |  | 5/22 This is completed 5/13 Created 915 comment flags. Request validation. 4/15 AbbaDox following on patient flags not visible in comments | 2026-05-13 | MANA | Completed
2 | Data Migration |  |  | Report migration is on-going |  | 2/11 | AbbaDox | In Progress
| Data Migration |  |  |  | 8/11 Migration has been kicked off. Determine ETA on Completion. 8/6 Reprocessing has taken place however there's one template that needs to be reviewed. Requested new Sample patient for the reprocessing. 8/6 AbbaDox updating ORU by location and templates with MANA's feedback. Pending on samples to review. 7/31 AbbaDox updated migration templates to include signatures for IC. The BC will not pusue signatures. Carrie reaching out to Jeff regarding ORU format for historical migration. This is holding up migration. AbbaDox to hurdle internally and determine in Header in ORU can be removed. 7/22 There's a need to touch base with Merge to determine if ORUs updated to not reflect header in body and to categorize samples so that IC and BC can see samples. 7/22 Reviwing sample reports AbbaDox commented that we are unable to modify the ORU message from Merge, as the header start and end points aren't consistently identifiable within the message format. 7/15 AbbaDox finalizing setup of Report template to then kick off migration. 7/8 Darron will resend copy of template. 7/2 Ruben to follow up on ticket with Interoperability 6/10 Templeta sent to Mayelin for review and potentially update. This wii allow to kick off migrration. 6/3 This is in Progress 5/27 Darron and Lisa to circleback. 5/22 Template shared with Darron as requested. 5/13 AbbaDox follwing on others clients that are also acredited with ACR. 5/13 MANA circling for confimation, it appears that logo is required. File will need to be less than 50KB. 5/13 Follow up with Denice on removing logo to decrease size of file. 4/29 Same update 4/22 MANA has provided all files. AbbaDox updating templates before starting migration. 4/16 Follow call with Craig tomorrow at 9.00 EST 4/15 Naheel requesting assistance from Craig to migrate data 4/1 Needs attention. | 2026-08-12 | AbbaDox | In Progress
| Data Migration |  |  | Future exams migration |  |  |  | In Progress
| Data Migration |  |  | Future exams Samples | 7/22 Future exam are ready for upload. 7/15 Meeting at 2.00 PM 7/8 Meeting with Paul to review updates. 7/2 Carrie and Paul have been working samples. Innitial looked good but need to consider another scenario. 6/26 Data Migration being reviewed with Paul 6/10 Carrie to updated crosswalk column C by adding the Complex procedure name. 6/10 Jeff to provide Merge complex/combo codes → Paul builds Excel crosswalk → Carrie maps to AbbaDox codes → Paul creates MagView grouping templates (must complete before next test patients). 6/3 Carrie reached to Jeff for futher assistance. Also, tracking conversation with Magview. 5/27 Meeting with Paul to review data. 5/20 Darron/Carrie to coodinate a call with Paul/Jeff/Craig/Carrie/Darron regarding the use of exam code vs. CPT code / Procedures in the way that it is coming across the interface 5/13 The combo codes from Merge return as individual exam codes with separate accession numbers, unlike our version, since each accession number generates a unique appointment ID in our migration. 4/29 Samples provided to AbbaDox, Paul requesting extract from Merge to then upload samples to AbbaDox for validation. 4/22 Met with Paul on Friday to discuss of future exams for BC. BC to create a test exams that Jeff could then download and provide to Abbaox 4/15 Data Services team are in communication with Jeff Yates at Merge and are ready for migration of future exams. | 2026-07-22 | AbbaDox | In Progress
1 | Account Configurations
2 | IC |  |  | MANA - IC Rules updates |  |  | AbbaDox | 100%
|  |  |  | Generic List of Values Update | 7/2 Updated accordingly, confirmed with Brittany that interface is working as expected. 6/26 Updated misaligned list. Need to add additional procedures in via upload tool. 6/10 AbbaDox added updated all local procedures with modifiers, eliminating the need for one of the GLV. AbbaDox. AbbaDox also added 6/3 This is on going 5/22 AbbaDox has updated the GLV for the Imaging Center by adding-26 to a list of procedures. Pending to update another list to finalize DFT testing. So far 3 of 5 of scenarios have passed. 5/13 Interface appears to be working as expected. There's a need to add more intstances to generic list of values. 4/22 All lists created. AbbaDox uploading to Careflow so that interface logic could be configured and tested. 4/8 Redefined billing interface requirement. Need to apply update. 4/1 Apply billing interface logic requested by Imaging Center | 2026-07-02 |  | Completed
[5 empty] | 4/1 IC will adopt proposed workflow of Foreign films via scheduling wizard |  |  | Completed
[5 empty] | 4/22 Form built to IC abandoning effort. 4/15 AbbaDox to enable eForm to capture discarded contrast | 2026-04-15 | AbbaDox | N/A
7/22 Met with Dawn and lined out all of the requirements. Only one update left related to the dictated letters order creation. 7/15 Update require to Room availability to display refine Foreign films workflow.
|  |  |  | Manual Distribution | 4/29 Retrigger of ORU | 2026-04-29 | AbbaDox | Completed
2 | BC
|  |  | IN-3684 | Medicare e2 to CPT | 7/2 This is completed 6/26 Follow up on testing 6/16 Made updates on call and tested succesfully. There's need to consider Supplment insurances on the GLV. 6/16 Issue fixed, GLV updated - ready for testing. 6/10 Tested G-Code update interface logic, AbbaDox appears to be adding incorrect Payer code to the interface logic. There's also a need to update the Payer Codes in the list of values as the ones provided do not match those in AbbaDox and eCW. 6/3 Request for logic update submitted to Interoperability 5/27 G-code required as an add on, not a replacement to the CPT. AbbaDox would need to include in the HL7. Two CPT codes to be considered on this logic. Review email from the Darron. Kim confirmed only one code. crosswalk provided 5/27 Working with Darrona and Kim Mayer on confirming G-codes 5/22 Need to confirm G-Codes wih MANA. 5/13 Request Submitted, pending Configuration 5/6 List sent to AbbaDox, proceed to map Federal payers to G-codes. Follow up on previous meeting minutes for further instructions. Provide list of federal payers (Medicare, VA) and their payer IDs from AbbaDox settings | 2026-06-10 | Kim M | Completed
[5 empty] | Provide list of CPT codes and corresponding G-codes to be swapped | 2026-04-29 | Kim M | Completed
[5 empty] | Load G-codes (e.g., G0279) into AbbaDox local modifiers table | 2026-04-29 | AbbaDox | Complete
1 | Bugs
3 | Account Configurations |  | BUG-2722 | Combo Code Bug | 4/1 Combo code bug fixed. Requires test with client. | 2026-04-01 |  | Completed
2 | BC |  |  | MANA - BC Rules updates | Reference Bug Tracker Tab |  | AbbaDox
| Account Configurations |  | BUG-2723 (PVS-957) | Complex Procedure – One Sub-Procedure Missing Description in Parent Appointment Section After Changing Procedure | 5/22 Ticket in defined status, being worked on by Dev. 5/13 Issue is defined and in development queue 4/1 Escalated | 2026-05-22 |  | Duplicate
|  |  | BUG-2808 | Combo Procedure – Procedure Missing Accession ID After Changing from Complex to Combo via Manage Procedures & Services | 5/22 Bug in development queue and assigned to developer 5/13 Issue is in development queue 4/1 Escalated 4/15 Bug found where Child procedurein Combo does NOT display an Accession ID after changed | 2026-05-22 |  | Duplicate
|  |  | BUG-2785 | Display minutes since last update | 5/22 5/22 Prioritization in progress 5/13 Pending resource assignment 4/15/2026 AbbaDox adding 60 minutes to minute count | 2026-05-13 |  | Duplicate
|  |  | BUG-2875 | Cancelled procedure persists in scheduling wizard when adding a new procedure to the same visit | 5/22 Prioritization in progress 5/13 Reproduced issue with MANA on Friday 5/7. Need to finalize ticket | 2026-05-22 |  | Duplicate
|  |  | BUG-2873 | Scheduling Rules Canceling Each Other Out | 5/22 Same update 5/13 Issue is in development queue 4/29 4/21 when canceling an exam and adding a new one to same visit. Ticket required for follow up. | 2026-05-22 |  | Duplicate
|  |  |  | Funcitionality that minimizes the duration of second in complex to 0 | 6/26 Pending Review 5/26 Follow up with Rafa D. |  |  | Duplicate
1 | Enhancement
2 | Account Configurations |  |  | Request to use 'New' Status when appointment is Rescheduled | Ticket requirement | 2/4 | AbbaDox | New
2 | Account Configurations |  | Feature-725 | Enhancement: Recurrent Block Slots |  | 11/26 | AbbaDox | Completed
2 | Account Configurations |  |  | Enhancement: Request to not have all locations selected when scheduling by default | Ticket requirement | 12/1 | AbbaDox | New
2 | Account Configurations |  |  | Enhancement: Payer and Assignment by Region |  | 3/18 | AbbaDox | Completed
1 | Analytics
2 | Analytics |  | AN-1977 | Setup Automated Monthly Reports – RAD Total, Coder Reports, Karas Location Procedure Counts |  | 3/18 | AbbaDox | In Progress
2 | Analytics |  | AN-2004 | Procedure Summary Report | 4/8 Update to report is now available in production for review. | 2026-04-08 | AbbaDox | Completed
[5 empty] | 4/15 Follow up required | 2026-04-15 | AbbaDox | In Progress
Note on I45: Ruben Gonzalez: Task will remain In Progress until cutover
Note on I46: Ruben Gonzalez: Task will remain In Progress until cutover
Note on I47: Ruben Gonzalez: Task will remain In Progress until cutover
Note on I48: Ruben Gonzalez: Task will remain In Progress until cutover