MANA / AbbaDox

| Meeting Date: | Wednesday, January 7, 2026 | Meeting Time | 10:00 AM EST |
| --- | --- | --- | --- |
| Location: | Teams Meeting |  |  |
| Facilitator | Join the meeting now Meeting ID: 281 654 499 189 Passcode: Hs2Ho7tm |  |  |

SharePoint Link: MANA – AbbaDox Careflow RIS SharePoint
Account Setup Workbook: MANA Account Setup Workbook

|  | Attendee | Party |
| --- | --- | --- |
| ☒ | Carrie Johnson | MANA |
| ☒ | Darron Mitchell | MANA |
| ☒ | Daniel Lad | MANA |
| ☒ | Dawn | MANA |
| ☒ | Ruben Gonzalez | AbbaDox |
| ☐ | Andreina Boudle | AbbaDox |
| ☐ | Rafael De Leon | AbbaDox |

- 7+ Locations, 120,000 Annual Studies

Meeting Minute

- Go Live Date Tentative - 2/24 - On-site assessment - 1/7 On-site Agenda confirmed - Workflow Reviews - A-Z Workflow Recap - IC – Completed - 11/5 Action: Ticket request being written, AbbaDox – Completed - 1/21 Discussion required - UAT - IC 12/31 - 12/31 Order Intake – In Progress - 1/5 Pending and Scheduling – In Progress - BC 12/31 - 12/31 Order Intake – Completed - 12/31 Pending and Scheduling – Completed - 12/31 Registration – Completed - 12/31 Technologist – In Progress - Interfaces Feature-707 - Merge PACS. Scope: Uni. ORM,ADT,ORU Thursdays at 3.00 PM EST. 100% - 12/31 AbbaDox is sending all messages, and interface is enabled. - MagView. Scope: Bid. ORM,ADT/ORU Tuesdays at 12.00 PM EST 90% - 12/31 ORU received, further testing required. - 12/31 Combo procedure management to be reviewed by Carrie, MANA – In Progress - 1/7 Full loop completed, AbbaDox reviewing IB ORU and validation on report, AbbaDox - New - PowerScribe. Scope: Bid. ORM,ADT/ORU - Thursday at 12.00 PM EST 90% - 12/17 AbbaDox uploading updated Imaging procedures to resume testing with PET. - 12/31 Rooms created for scheduling testing but require further review with Dawn, AbbaDox - New - eCW. Scope: Bid. ORU,ADT,DFT,SIU/ORM, ADT (Steven Dominguez) Thursday at 2.00 PM EST 25% - 12/31 eCW requires AbbaDox Local Procedures Compendium, AbbaDox - Completed - 12/31 Submitting function in eCW almost ready for eCW, pending on Compendium and Cancellation workflow - 12/31 Report in embedded PDF can be sent in OB ORU from AbbaDox to eCW. - Outreads Flatiron/OncoEMR HOG 5% - 12/31 AbbaDox to return signed BAA from HOG/OncoEMR, AbbaDox – Completed - 1/7 AbbaDox is ready to revamp interface, AbbaDox - New - Data Migration DS-696 - Scope: Merge .CSV Data upload template. Pt records with payers, historical exams, future exams, historical ORU. - 12/31 Data migration has begun, AbbaDox reviewing patient records and determined 940 duplicates in file. - 1/5 In Progress - Account Configurations ETA: 12/5 - Block FAB Feature-725 - 11/26 Ticket is on-going. - 12/1 Inquiry: In wizard, request to not have all locations selected when scheduling by default, AbbaDox – New - 12/31 Configuration for Foreign Films and dictated letters – In Progress - 12/31 Follow up on findings determined in the UAT for the BC, AbbaDox – In progress - Document Management - Reforma (Print) – No need Reforma Barcode - IC 9/18 Upload registration documents to Reforma folder in Sharepoint. - 12/17 AbbaDox uploading additional forms to Reforma, AbbaDox – In progress - BC 10/1 will pursue Reforma to print Router, Recommendation, and Risk Assessment - 11/26 Documents have been loaded, packages being built, AbbaDox - In progress