MANA / AbbaDox

| Meeting Date: | Wednesday, January 28, 2026 | Meeting Time | 10:00 AM EST |
| --- | --- | --- | --- |
| Location: | Teams Meeting |  |  |
| Facilitator | Join the meeting now Meeting ID: 281 654 499 189 Passcode: Hs2Ho7tm |  |  |

SharePoint Link: MANA – AbbaDox Careflow RIS SharePoint
Account Setup Workbook: MANA Account Setup Workbook

|  | Attendee | Party |
| --- | --- | --- |
| ☒ | Carrie Johnson | MANA |
| ☒ | Darron Mitchell | MANA |
| ☒ | Daniel Lad | MANA |
| ☒ | Dawn | MANA |
| ☒ | Ruben Gonzalez | AbbaDox |
| ☐ | Andreina Boudle | AbbaDox |
| ☐ | Rafael De Leon | AbbaDox |

- 7+ Locations, 120,000 Annual Studies

Meeting Minute

- Go Live Date Tentative - 2/24 - Workflow Reviews - A-Z Workflow Recap - IC – Completed - 11/5 Action: Ticket request being written, AbbaDox – Completed - 1/21 Discussion required – 1/28 – Completed - 1/28 Caveat on PS Interface where order in AbbaDox may need allowed to read unless is marked as TechCompleted in AbbaDox, Carrie/Dawn will test workflow and determine if further conversation is required, MANA - New - UAT - IC 12/31 - 1/21 Billing Workflow discussion required, AbbaDox – Completed - 1/28 Schedule call with Imaging Specialists for feedback on billing workflow Transmit button, AbbaDox – New - 1/28 Schedule mock workflow session with Lee Ester, AbbaDox – New - 1/28 Include MANA into this request RT-789 - BC 12/31 - 12/31 Order Intake – Completed - 12/31 Pending and Scheduling – Completed - 12/31 Registration – Completed - 12/31 Technologist – Completed - 1/21 Billing Workflow Review on 1/23 – Completed - 1/28 Carrie to confirm with Kim sign-off on workflow, MANA - New - Interfaces Feature-707 - Merge PACS. Scope: Uni. ORM,ADT,ORU Thursdays at 3.00 PM EST. 100% - 12/31 AbbaDox is sending all messages, and interface is enabled. - MagView. Scope: Bid. ORM,ADT/ORU Tuesdays at 12.00 PM EST 90% - 1/7 Full loop completed, AbbaDox reviewing IB ORU and validation on report, AbbaDox – New - 1/21 Recent issues: - Complex procedures rescheduling issue (AbbaDox not sending cancellation message for ungroup complex procedures), AbbaDox – Completed - 1/28 Trigger takes place upon appointment status update. - Addendum follow up required, AbbaDox – New - Filter required for ADT, only send ADT when appointment is scheduled in breast center location, AbbaDox – In Progress – Confirm status with Carrie - PowerScribe. Scope: Bid. ORM,ADT/ORU - Thursday at 12.00 PM EST 100% - 1/21 Issue determined, need to build updates rooms and create procedures under modality PT – Completed - eCW. Scope: Bid. ORU,ADT,DFT,SIU/ORM, ADT (Steven Dominguez) Thursday at 2.00 PM EST 40% - 12/31 Report in embedded PDF can be sent in OB ORU from AbbaDox to eCW. - 1/21 HOG Results to be delayed to eCW confirmed, AbbaDox - Completed - 1/21 Mapping of Location/Rooms required, AbbaDox – In Progress - 1/28 Require assistance from MANA - 1/21 AbbaDox compendium to eCW must refined to only the procedures that will ever be submitted from eCW. Current compendium also has procedures required for migration, AbbaDox – New - 1/21 Modality in AbbaDox needs to be mapped to visit type in eCW, AbbaDox/eCW - New - Outreads Flatiron/OncoEMR HOG 5% - 12/31 AbbaDox to return signed BAA from HOG/OncoEMR, AbbaDox – Completed - 1/7 AbbaDox is ready to revamp interface, AbbaDox – In Progress - Hollogic - 1/28 New instance, may require unidirectional OB ORM and ADT interface. - 1/28 Reach out Hollogic regarding request to build interface with AbbaDox, MANA - New - Data Migration DS-696 - Scope: Merge .CSV Data upload template. Pt records with payers, historical exams, future exams, historical ORU. - 1/21 Discuss duplicate patients and Room Mapping - 1/21 MANA cleaned up patients in eCW, Merge to share new data upload to AbbaDox. - 1/21 MANA to assist on room mapping file in Sharepoint, MANA - New - Account Configurations ETA: 12/5 - 12/31 Configuration for Foreign Films and dictated letters – Completed - 1/28 IC will adopt propose workflow via scheduling wizard - 1/28 Bug tickets reported by BC are being prioritized this week. - Enhancement: - 11/26 FAB Feature-725 - 12/1 Inquiry: In wizard, request to not have all locations selected when scheduling by default, AbbaDox – New - Document Management - Reforma (Print) – No need Reforma Barcode - IC 1/21 New forms available for upload - 1/21 BC – Reforma - Completed