MANA / AbbaDox

| Meeting Date: | Wednesday, February 18, 2026 | Meeting Time | 10:00 AM EST |
| --- | --- | --- | --- |
| Location: | Teams Meeting |  |  |
| Facilitator | Join the meeting now Meeting ID: 281 654 499 189 Passcode: Hs2Ho7tm |  |  |

SharePoint Link: MANA – AbbaDox Careflow RIS SharePoint
Account Setup Workbook: MANA Account Setup Workbook

|  | Attendee | Party |
| --- | --- | --- |
| ☒ | Carrie Johnson | MANA |
| ☒ | Darron Mitchell | MANA |
| ☒ | Daniel Lad | MANA |
| ☒ | Dawn | MANA |
| ☒ | Ruben Gonzalez | AbbaDox |
| ☐ | Andreina Boudle | AbbaDox |
| ☐ | Rafael De Leon | AbbaDox |

- 7+ Locations, 120,000 Annual Studies

Meeting Minute

- Go Live Date Tentative – 4/14 - 2/11 Pending feedback on Hollogic and Onco. - UAT - IC - 2/18 Update to worklist required per conversation on 2/12 - BC - 1/28 Carrie to confirm with Kim sign-off on Billing Workflow, MANA – In Progress - 2/18 Carrie planning to show full workflow to Kim before sign off. - Training - 2/12 Collateral for training one-to-one. - 2/18 Looped in Tyler Ricketts to being training prep, AbbaDox – In Progress - 2/18 Confirm that MANA has been added to the release notes, AbbaDox - New - Interfaces Feature-707 - Merge PACS. Scope: Uni. ORM,ADT,ORU 100% - MagView. Scope: Bid. ORM,ADT/ORU Tuesdays at 12.00 PM EST 90% - 2/11 Interface testing with all procedures, MANA – In Progress - PowerScribe. Scope: Bid. ORM,ADT/ORU - Thursday at 12.00 PM EST 100% - 2/4 Action: Foreign Films: Update OB logic to trigger ORM upon NEW appointment status, AbbaDox – In Progress - 2/4 Linked reports: Followed up with PS360 regarding this issue, update can be done by PS, PS – Completed - 2/18 AbbaDox reviewing update, AbbaDox - New - 2/4 Custom field follow up to PowerScribe, PS – Completed (No action needed) - eCW. Scope: Bid. ORU,ADT,DFT,SIU/ORM, ADT (Steven Dominguez) Thursday at 2.00 PM EST 40% - 2/11 Note: The last compendium provided is still good for eCW, AbbaDox has not created more procedures relevant to eCW, to be done closer to go live, AbbaDox - New - 2/4 Action: Request to not send OB SIU when order is created under a foreign film location, AbbaDox – In Progress - 2/4 Action: AbbaDox to account for Referring Practice NPI in OBR in ORU, AbbaDox – In Progress - 2/18 IB ORM/ADT and OB SIU is in place so MANA can begin testing this setup, MANA - New - 2/18 Steven pending on updates to DFT triggers to eCW, close the loop on the interface, AbbaDox – New - 2/26 Testing, AbbaDox - New - Outreads Flatiron/OncoEMR HOG 5% - 2/18 Interface discussions on-going via email, inquiry about SFTP drop, AbbaDox – In Progress - Hollogic - 2/4 Ticket submitted to Hollogic, scope being defined by Hollogic, Hollogic – Completed - 2/18 Quote received and signed, next step await resource assignment, Hollogic – In progress - Data Migration DS-696 - 2/11 MANA assisting on Merging patients, MANA – Completed - 2/18 Note: MANA to merge patients in Merge so that db is up to date before go live. - 2/11 Report migration is on-going, AbbaDox – In Progress Account Configurations - 1/28 IC will adopt propose workflow of Foreign films via scheduling wizard - 2/4 AbbaDox to update rooms, procedures and build rules to accomodate HOG and general scheduling rules, AbbaDox - In Progress - MANA - IC Rules updates.xlsx - 1/28 Bug tickets reported by BC are being prioritized this week. - Combo Code Bug - Change of Complex Procedure Bug - 2/11 Tickets revised with MANA and sent back to dev. - 2/4 Request to use “New” Status when appointment is Rescheduled, AbbaDox - New - Enhancement: - 11/26 Recurrent Block Slots - 12/1 Request to not have all locations selected when scheduling by default, AbbaDox – New - Document Management – Completed - Analytics - 2/26 RIS - Procedure Summary Report update - 2/26 Cadence of emailed reports