MANA / AbbaDox

| Meeting Date: | Wednesday, March 4, 2026 | Meeting Time | 10:00 AM EST |
| --- | --- | --- | --- |
| Location: | Teams Meeting |  |  |
| Facilitator | Join the meeting now Meeting ID: 281 654 499 189 Passcode: Hs2Ho7tm |  |  |

SharePoint Link: MANA – AbbaDox Careflow RIS SharePoint
Account Setup Workbook: MANA Account Setup Workbook

|  | Attendee | Party |
| --- | --- | --- |
| ☒ | Carrie Johnson | MANA |
| ☒ | Darron Mitchell | MANA |
| ☒ | Daniel Lad | MANA |
| ☒ | Dawn | MANA |
| ☒ | Ruben Gonzalez | AbbaDox |
| ☐ | Andreina Boudle | AbbaDox |
| ☐ | Rafael De Leon | AbbaDox |

- 7+ Locations, 120,000 Annual Studies

Meeting Minute

- Go Live Date Tentative – 4/14 - UAT - IC - 2/18 Update to worklist required per conversation on 2/12 - BC - 1/28 Carrie to confirm with Kim sign-off on Billing Workflow, MANA – In Progress - 2/18 Carrie planning to show full workflow to Kim before sign off. - Introduce April from Toledo MANA, AbbaDox - new - Training 3/30-4/3 - 2/12 Collateral for training one-to-one. - 2/18 Looped in Tyler Ricketts to being training prep, AbbaDox – In Progress - 2/18 Confirm that MANA has been added to the release notes, AbbaDox - New - Interfaces Feature-707 - Merge PACS. Scope: Uni. ORM,ADT,ORU 100% - PowerScribe. Scope: Bid. ORM,ADT/ORU - Thursday at 12.00 PM EST 100% - MagView. Scope: Bid. ORM,ADT/ORU Tuesdays at 12.00 PM EST 90% - 2/11 Interface testing with all procedures, MANA – In Progress - eCW. Scope: Bid. ORU,ADT,DFT,SIU/ORM, ADT (Steven Dominguez) Thursday at 2.00 PM EST 40% - 2/11 Note: The last compendium provided is still good for eCW, AbbaDox has not created more procedures relevant to eCW, to be done closer to go live, AbbaDox - New - 2/4 Action: Request to not send OB SIU when order is created under a foreign film location, AbbaDox – In Progress - 2/4 Action: AbbaDox to account for Referring Practice NPI in OBR in ORU, AbbaDox – In Progress - 2/18 IB ORM/ADT and OB SIU is in place so MANA can begin testing this setup, MANA - New - 2/18 Steven pending on updates to DFT triggers to eCW, close the loop on the interface, AbbaDox – New - 2/26 Testing, AbbaDox - New - Outreads Flatiron/OncoEMR HOG 5% - 2/18 Interface discussions on-going via email, inquiry about SFTP drop, AbbaDox – In Progress - 3/4 Similar update, added Naheel to discussion for assistance, AbbaDox – In Progress - Hologic - 3/4 Samples received from Hologic, AbbaDox – In Progress - Data Migration DS-696 - 2/11 MANA assisting on Merging patients, MANA – Completed - 2/18 Note: MANA to merge patients in Merge so that db is up to date before go live. - 2/11 Report migration is on-going, AbbaDox – In Progress - 3/4 Note: eCW patients in Merge that require merging. MANA will not merge in eCW, but rather in AbbaDox. In the meantime, MANA will keep list of patients that require merging and provide to AbbaDox prior to go live. Account Configurations - 1/28 IC will adopt propose workflow of Foreign films via scheduling wizard - 3/4 MANA - IC Rules updates.xlsx , AbbaDox – In progress - 1/28 Bug tickets reported by BC are being prioritized this week. - Combo Code Bug - Change of Complex Procedure Bug - 2/11 Tickets revised with MANA and sent back to dev. - 2/4 Request to use “New” Status when appointment is Rescheduled, AbbaDox – New - 3/4 Enable Regionalization so that users can see all patients while considering location restrictions, AbbaDox – In Progress - Enhancement: - 11/26 Recurrent Block Slots - 12/1 Request to not have all locations selected when scheduling by default, AbbaDox – New - Analytics - 2/26 RIS - Procedure Summary Report update - 2/26 Cadence of emailed reports - 3/4 Follow up on Analytics required updates, AbbaDox - New