MANA / AbbaDox

| Meeting Date: | Wednesday, March 18, 2026 | Meeting Time | 10:00 AM EST |
| --- | --- | --- | --- |
| Location: | Teams Meeting |  |  |
| Facilitator | Join the meeting now Meeting ID: 281 654 499 189 Passcode: Hs2Ho7tm |  |  |

SharePoint Link: MANA – AbbaDox Careflow RIS SharePoint
Account Setup Workbook: MANA Account Setup Workbook

|  | Attendee | Party |
| --- | --- | --- |
| ☒ | Carrie Johnson | MANA |
| ☒ | Darron Mitchell | MANA |
| ☒ | Daniel Lad | MANA |
| ☒ | Dawn | MANA |
| ☒ | Ruben Gonzalez | AbbaDox |
| ☐ | Andreina Boudle | AbbaDox |
| ☐ | Rafael De Leon | AbbaDox |

- 7+ Locations, 120,000 Annual Studies

Meeting Minute

- Go Live Date Tentative – 4/14 - UAT - IC - 2/18 Update to worklist required per conversation on 2/12 - BC - 1/28 Carrie to confirm with Kim sign-off on Billing Workflow, MANA – In Progress - 2/18 Carrie planning to show full workflow to Kim before sign off. - Training - 4/6 - 3/11 Discuss training plan with Tyler on 3/18 - Completed - Interfaces Feature-707 - Merge PACS. Scope: Uni. ORM,ADT,ORU 100% - PowerScribe. Scope: Bid. ORM,ADT/ORU - Thursday at 12.00 PM EST 100% - 3/18 FF Results not processing in AbbaDox if appt. is not in TechComplete status, AbbaDox - New - MagView. Scope: Bid. ORM,ADT/ORU Tuesdays at 12.00 PM EST 90% - 2/11 Interface testing with all procedures, MANA – In Progress - eCW. Scope: Bid. ORU,ADT,DFT,SIU/ORM, ADT (Steven Dominguez) Thursday at 2.00 PM EST 70% - 2/11 Note: The last compendium provided is still good for eCW, AbbaDox has not created more procedures relevant to eCW, to be done closer to go live, AbbaDox - New - 3/18 Action: Test that AbbaDox does not send OB SIU when order is created under a foreign film location, MANA – In Progress - 2/4 Action: AbbaDox to account for Referring Practice NPI in OBR in ORU and DFT, Steven – In Progress - 2/18 IB ORM/ADT and OB SIU is in place so MANA can begin testing this setup, MANA – In Progress - 3/18 External resource mapping, AbbaDox - Completed - Outreads Flatiron/OncoEMR HOG 20% - 3/18 AbbaDox dropping messages in the sFTP, AbbaDox – In Progress - Hologic 85% - 3/18 Hologic interface appears to be enabled, testing is ongoing, MANA – In Progress - Data Migration DS-696 - 2/11 MANA assisting on Merging patients, MANA – Completed - 3/4 Note: eCW patients in Merge that require merging. MANA will not merge in eCW, but rather in AbbaDox. In the meantime, MANA will keep list of patients that require merging and provide to AbbaDox prior to go live. - 2/11 Report migration is on-going, AbbaDox – In Progress Account Configurations - 1/28 IC will adopt propose workflow of Foreign films via scheduling wizard - 3/4 MANA - IC Rules updates.xlsx, AbbaDox – In progress - 1/28 Bug tickets reported by BC are being prioritized this week. - Comdbo Code Bug - Change of Complex Procedure Bug - 2/11 Tickets revised with MANA and sent back to dev. - 2/4 Request to use “New” Status when appointment is Rescheduled, AbbaDox – In Progress - 3/18 Ticket requirement, AbbaDox - New - Enhancement: - 11/26 Recurrent Block Slots - 12/1 Request to not have all locations selected when scheduling by default, AbbaDox – New - 3/18 Payer and Assignment by Region, AbbaDox - New - Analytics - Setup Automated Monthly Reports - RAD Total, Coder Reports, and Karas Location Procedure Counts - AN-1977 - Procedure Summary Report - AN-2004 - 3/18 Analytics build, AbbaDox – In Progress