MANA / AbbaDox

| Meeting Date: | Thursday, September 18, 2025 | Meeting Time | 10:00 AM EST |
| --- | --- | --- | --- |
| Location: | Teams Meeting |  |  |
| Facilitator | Join the meeting now Meeting ID: 281 654 499 189 Passcode: Hs2Ho7tm |  |  |

SharePoint Link: MANA – AbbaDox Careflow RIS SharePoint
Account Setup Workbook: MANA Account Setup Workbook

|  | Attendee | Party |
| --- | --- | --- |
| ☒ | Carrie Johnson | MANA |
| ☒ | Darron Mitchell | MANA |
| ☒ | Daniel Lad | MANA |
| ☒ | Dawn | MANA |
| ☒ | Ruben Gonzalez | AbbaDox |
| ☐ | Andreina Boudle | AbbaDox |
| ☐ | Rafael De Leon | AbbaDox |

- 7+ Locations, 120,000 Annual Studies

Meeting Minute

- Workflow Reviews - Technologist - IC 9/25 – New - BC 9/11 – Completed - Billing - IC 10/02 Review - New - BC 9/19 Review - Completed - Interfaces Feature-707 - 9/3 VPN: Same VPN will be used for Merge, MagView, PW and OnceEMR - Completed - Merge PA/CS. Scope: Uni. ORM,ADT,ORU - 9/24 Kick-off on 9/25 - MagView. Scope: Bid. ORM,ADT/ORU - 9/18 Pending on PM assignment, MV - In Progress - PowerScribe. Scope: Bid. ORM,ADT/ORU - 9/24 Kick-off on 9/24 - eCW. Scope: Bid. ORU,ADT,DFT,SIU/ADT (Steven Dominguez) - 9/18 Request assist to Steven to open ticket with eCW. - Outreads - 9/3 OncoEMR working on agreement, the Engineer Assignment. Timeline completion 2 months. - 9/18 Kick-off completed. OncoEMR to share SOW with HOG. - Data Migration DS-696 - Scope: Merge .CSV Data upload template. Pt records with payers, historical exams, future exams, historical ORU. - 9/11 Access to SFTP shared with Jeff at Merge, AbbaDox – Completed - 9/11 AbbaDox pending on samples from Merge, AbbaDox - New - Account Configurations - 9/18 Need to schedule configuration call with the Imaging Center, Dawn, Lynette, and Britney. - Questionnaires - IC 9/18 Review, IC – In Progress - BC 9/3 AbbaDox to build Questionnaire provided, AbbaDox – In Progress - Resource Scheduling Rules - IC 9/18 Review – New - BC 9/3, 9/15, 9/29 Review – In Progress - Notification Slots - IC – New - BC 9/29 Review – In Progress - Complex Scheduling Rules - IC 9/18 Review – New - BC 9/29 Review – Completed - Reforma - IC 9/18 Review – In Progress - BC 9/19 Review – In Progress - Document Management - Reforma (Print) - 9/11 BC will pursue Reforma to print Router. - IC 9/18 Upload registration documents to Reforma folder in Sharepoint. - ScanDox (ScanDox not required .)