MANA / AbbaDox

| Meeting Date: | Wednesday, October 22, 2025 | Meeting Time | 10:00 AM EST |
| --- | --- | --- | --- |
| Location: | Teams Meeting |  |  |
| Facilitator | Join the meeting now Meeting ID: 281 654 499 189 Passcode: Hs2Ho7tm |  |  |

SharePoint Link: MANA – AbbaDox Careflow RIS SharePoint
Account Setup Workbook: MANA Account Setup Workbook

|  | Attendee | Party |
| --- | --- | --- |
| ☒ | Carrie Johnson | MANA |
| ☒ | Darron Mitchell | MANA |
| ☒ | Daniel Lad | MANA |
| ☒ | Dawn | MANA |
| ☒ | Ruben Gonzalez | AbbaDox |
| ☐ | Andreina Boudle | AbbaDox |
| ☐ | Rafael De Leon | AbbaDox |

- 7+ Locations, 120,000 Annual Studies

Meeting Minute

- Workflow Reviews - Task Management Worklist - 10/18 – New - A-Z Workflow Recap - IC 10/16 – In Progress - 10/29 Update to Order Intake processes. - BC 10/29 – In Progress - Interfaces Feature-707 - Merge PACS. Scope: Uni. ORM,ADT,ORU Thursdays at 3.00 PM EST. 80% - 10/29 Testing is in progress. AbbaDox is creating orders for all service types used at the Imaging Center. Next step is to request client to link images to study. - MagView. Scope: Bid. ORM,ADT/ORU Tuesdays at 12.00 PM EST - 10/29 Interface build is in progress via email communication, AbbaDox has received has sent ORM and received ORU. - PowerScribe. Scope: Bid. ORM,ADT/ORU - Thursday at 12.00 PM EST 70% - 10/22 AbbaDox is ready to receive report/ORU to test IB Interface. - 10/29 Noticed via email an issue with connectivity on Friday, AbbaDox pending ORU. - eCW. Scope: Bid. ORU,ADT,DFT,SIU/ADT (Steven Dominguez) Thursday at 2.00 PM EST - 10/29 Weekly kick-off on Thursday at 2.00 PM EST. - Outreads Flatiron/OncoEMR HOG - 10/1 Pending on PM assignment, Flatiron- In Progress. ETA 10/15 - 10/29 Service order is still in compliance. - Data Migration DS-696 - Scope: Merge .CSV Data upload template. Pt records with payers, historical exams, future exams, historical ORU. - 10/29 AbbaDox has reached to Merge for Sample messages to kick-off migration. - Account Configurations - Combo Codes - IC 10/1 - Completed - BC 10/1 - Completed - Questionnaires - IC 9/18 Review, IC – 10/13 Completed - BC 10/15 – Completed - Resource Scheduling Rules - IC 9/18 Review – New - BC 9/3, 9/15, 9/29 Review – In Progress - Notification Slots - IC Completed - BC Completed - Complex Scheduling Rules - IC 9/18 Review – Completed (Not used in the imaging Center) - BC 9/29 Review – Completed - Reforma - IC 9/18 Review – Complete - BC 9/19 Review – Complete - Rooms and Resources - IC – 10/22 - Completed - BC – 10/15 Completed - Patient Chart - 10/15 There’s a need to define the “look” of the patient chart. - Edit Report Functionality - IC 10/23 To be reviewed - BC 10/23 To be reviewed - Task Management - IC 10/27 Completed - BC 10/24 Completed - Local Procedures - 10/8 IC – AbbaDox to review MRI procedures missing in Local Procedures, AbbaDox – Completed - 10/22 IC – MRI are up to date but missing Xrays, AbbaDox – Completed - 10/29 IC – Xrays available under modality of DX. - Document Management - Reforma (Print) - IC 9/18 Upload registration documents to Reforma folder in Sharepoint. - 10/1 Documents available in Sharepoint, AbbaDox – In Progress - BC 10/1 will pursue Reforma to print Router, Recommendation, and Risk Assessment - 10/1 Documents available in Sharepoint, AbbaDox – In Progress