## Bugs & Issues Log
Test ID | Section | Priority | Type | Go Live Requirement | Test Scenario | Details / Notes | Tickets
SCH-005 | 2. Pending Appts & Scheduling | Medium | Enhancement | No | Confirm patient details in scheduling wizard | 4/10 AbbaDox following this setting. Ability to change patient demographics should not be available in Wizard and Careflow overall. Status: Fail. | https://pinkypixels.atlassian.net/browse/DEVOPS-1021
SCH-006 | 2. Pending Appts & Scheduling | Low | Enhancement | No | Call patient and patient answers - proceed to calendar | 4/10 Continue follow up on this enhancement. Location dropdown defaults to ALL; Client would prefer it defaults to None.
SCH-011 | 2. Pending Appts & Scheduling | Low | Enhancement | No | Update pending reason after 2nd contact attempt | Enhancement: Can window be closed or prompt be provided after updating pending reason. Can updating pending reason behave the same way when updating to initial pending reason where wizard moves to Confirmation.
SCH-013 | 2. Pending Appts & Scheduling | Medium | Configuration | No | Update pending reason when unable to schedule | 4/7 Generate Outbound Fax upon Updating to Pending Reason - BC Unable to Contact Ticket AB-741 | https://pinkypixels.atlassian.net/browse/AB-741
SCH-014 | 2. Pending Appts & Scheduling | Medium | Enhancement | No | Verify scheduling rules point to correct locations/rooms | 4/10 Issue: A patient may have visits in both IC and BC. If the last comment entered is the one visible in the worklist, the BC may get confused by comment entered by imaging center. Request: Create setting where comment in worklist is the one entered for the visit, not the last comment. | Ticket Required
REG-009 | 3. Registration | High | Configuration | Yes | Print Router from Careflow RIS | 4/14 Completed 4/10 Form package printed out as expected, however AbbaDox will be adding more smartfields and will be removing barcode from the forms. There's need to add the Reforma DB fields. Status: Fail.
REG-010 | 3. Registration | Medium | Configuration | Yes | Print Router day before appointments | 4/10 Reforma prints out a document for every procedure in visit. It should instead print a document the visit the only, not per procedure. Toolbar Action Button for Reforma in Check In/Out. Status: Fail.
TECH-002 | 4. Technologist | High | Bug | Yes | Monitor for appointments with 'Arrive' status | 4/10 Timezone Issue Bug: Last modified date column displays and additional 60 minutes. Issue with minutes display. Enhancement: Also, turn red after an hour since last update. Status: Fail. | https://pinkypixels.atlassian.net/browse/BUG-2785
TECH-011 (Added while Testing) | 4. Technologist | Medium | Bug | Yes | Change Procedure | 4/10 Breast Center will not be using the Tech Workflow window, therefore will not be launching the technologist window. Still tracking bug around changing the Combo to complex. Status: Fail. Note: End here on 4/10. Will resume on 4/14. | https://pinkypixels.atlassian.net/browse/BUG-2723
| Scheduling | High | Bug | N/A | Order of Procedures don't visually match the accession number from Patient History | Patient’s History window from the Patient’s Chart, when an appointment has multiple procedures it is ordering the procedure and the accession numbers in a way that they don’t match. | https://pinkypixels.atlassian.net/browse/BUG-2797
| Hologic Interface | High | Enhancement | TBD | When a patient appointment is rescheduled in AbbaDox, the Accession ID and Visit ID in the outgoing HL7 message remain unchanged | 4/24/2026 Update AbbaDox to generate a new Accession ID on reschedule status to eliminate need for Hologic to upgrade | https://pinkypixels.atlassian.net/browse/IN-3508
LEGEND
Bug
Fail
Enhancement
Issue