## eCW_AbbaDox_Merge_PS360
Interface Testing Script — eCW, AbbaDox, Merge & PowerScribe360 (eCW Order Workflow)
Test Date: 3/26 |  | Tester: Ruben, Dawn, Craig |  | Environment: Prod |  | Build/Version:
Step | Sub | Test Step Description | Result (Pass/Fail) | Notes | Issue Found | Ticket #
1 |  | Open eCW | Pass
2 |  | Submit Order in eCW | Pass
| a | ↳ ORM is Sent from eCW to AbbaDox | Pass | ⚠ ORM includes eCW accession "7227A8969741"
3 |  | Open AbbaDox | Pass
4 |  | Select Patient Search and find patient record | Pass
5 |  | Open Patient History | Pass | MRN: 700397524
6 |  | eCW order is available under Pending Appointments | Pass
7 |  | Select Pending Appointment | Pass
8 |  | Schedule Pending Appointment |  | Note: AbbaDox appears to have automatically linked insurances.
9 |  | Appointment is scheduled in Imaging Center | Pass | Accession: 7227A8969756
| a | ↳ SIU message is sent from AbbaDox to eCW | Pass | Note: Noticed that provider in eCW reads "Reference Radiology", not David Clay. AbbaDox OB message reads David Clay.
| b | ↳ ORM is sent to Merge PACS | Pass
| c | ↳ ORM is sent to PowerScribe360 | Pass
10 |  | Open PowerScribe
11 |  | Dictate a Radiology report
| a | ↳ ORU is sent to AbbaDox
12 |  | Upon receiving report in AbbaDox, AbbaDox will send result upstream
| a | ↳ ORU is sent to Merge
| b | ↳ ORU is sent to eCW
13 |  | User will open Coding Worklist
14 |  | Identify the Completed appointment | Pass | ⚠ Completed Appointments contain a radiology report
15 |  | User update status to Billing Complete
| a | ↳ DFT is sent to eCW
TEST SUMMARY
Total Steps Tested
Total Passed
Total Failed
Overall Result
Tested By
Test Date
Sign-Off

## AbbaDox_Merge_Magview_Hologic
Interface Testing Script — AbbaDox, Merge, MagView & Hologic
Test Date: |  | Tester: |  | Environment: |  | Build/Version:
Step | Sub | Test Step Description | Result (Pass/Fail) | Notes | Issue Found | Ticket #
1 |  | Open AbbaDox
2 |  | Select Patient Search
3 |  | If Patient does not exist in AbbaDox
| a | ↳ Create patient in eCW
| b | ↳ ADT is sent to AbbaDox
| c | ↳ AbbaDox creates patient record
4 |  | Open Patient History
5 |  | Create New Appointment
6 |  | Appointment is scheduled Breast Center
| a | ↳ SIU message is sent from AbbaDox to eCW
| b | ↳ ORM is sent to Merge PACS
| c | ↳ ORM is sent to MagView
7 |  | Open MagView
8 |  | Dictate a Radiology report
| a | ↳ ORU is sent to AbbaDox
9 |  | Upon receiving report in AbbaDox, AbbaDox will send result upstream
| a | ↳ ORU is sent to Merge
| b | ↳ ORU is sent to eCW
10 |  | User will open Coding Worklist
11 |  | Identify the Completed appointment |  | ⚠ Completed Appointments contain a radiology report
12 |  | User update status to Billing Complete
| a | ↳ DFT is sent to eCW
TEST SUMMARY
Total Steps Tested
Total Passed
Total Failed
Overall Result
Tested By
Test Date
Sign-Off

## AbbaDox_eCW_Merge_OncoEMR
Interface Testing Script — AbbaDox, eCW, Merge & OncoEMR (Foreing Films)
Test Date: |  | Tester: Ruben, Dawn, and Brittney |  | Environment: |  | Build/Version:
Step | Sub | Test Step Description | Result (Pass/Fail) | Notes | Issue Found | Ticket #
1 |  | Open OncoEMR | Pass
2 |  | Identify order to be created in AbbaDox | Pass
3 |  | Open AbbaDox | Pass
4 |  | Select Patient Search | Pass
5 |  | If Patient does not exist in AbbaDox
| a | ↳ Create patient in eCW | Pass
| b | ↳ ADT is sent to AbbaDox | Pass
| c | ↳ AbbaDox creates patient record | Pass
6 |  | Select action button to Create New Appointment | Pass
7 |  | Open Scheduling Wizard | Pass
8 |  | Select Service type | Pass
9 |  | Select foreign film procedure | Pass | ⚠ Foreign Film procedures are identified with a "26" in exam code |  |  | Scheduled ztest, test for CT
10 |  | Appointment is scheduled Foreign Film Location
| a | ↳ ORM is sent to Merge PACS | Pass
| b | ↳ ORM is sent to PowerScribe360 | Pass
11 |  | Open PowerScribe360 | Pass
12 |  | Dictate a Radiology report
| a | ↳ ORU is sent to AbbaDox | Pass
13 |  | Upon receiving report in AbbaDox, AbbaDox will send result upstream | Pass
| a | ↳ ORU is sent to Merge | Pass
| b | ↳ ORU is sent to eCW |  | ⚠ ORU to eCW has a delay of 7 days |  |  | Added note to Calendar to check ECW in 7 days
| c | ↳ ORU is sent to OncoEMR | Pass | ⚠ This is an unsolicited ORU because ORM did not originate
14 |  | User will open Coding Worklist | Pass
15 |  | Identify the Completed appointment | Pass | ⚠ Completed Appointments contain a radiology report
16 |  | User update status to Billing Complete | Pass
| a | ↳ DFT is sent to eCW | Fail | ⚠ DFT would include "26" Modifier | It did go over to ECW but didn't have 26 in Column M1
TEST SUMMARY
Total Steps Tested
Total Passed
Total Failed
Overall Result
Tested By
Test Date
Sign-Off

## DFT Testing
Generic List | Use Case | Accession | Pass/Fail | Note | Story Description
Add Diagnosis for Exam in Location | If exam scheduled in specific location, add diagnosis to visit. | AB4792 | Pass | 5/7 1. Dummy was successfully added to visit. 5/7 2. the meantime, Ruben Added 73130BILAT-26 to PWHC in GLV. 5/7 Note: There's a need to include the "sister" procedures that include "-26" | When an exam code is scheduled in one of the Karas and Patt Walker locations, AbbaDox is automatically applying the "Dummy" diagnosis to the procedure on the visit. This is AbbaDox logic that does not yet impact interfaces. In other words, when I schedule an exam from this list into the Karas or PW location, AbbaDox add a Dummy diagnosis.
DFT Exam Location Diag Modifer Mapping | If procedure matches identifier, and location matches Link to Category , link identifier will be sent as modifier in FT1.26. Description = Diagnosis | AB4792 | Pass | 5/7 3. Because case in row #2.2 worked, and dummy was applied to visit, Ruben created 73130BILAT-26 in this GLV to test the interface, to confirm 26 modifier (linked identified) is sent. Brittany is working with Matt to generate a report. Upon receving report, Britt will update to billing completed. Exepectation is for 26 modifier to be sent in interface. 5/11 4. AbbaDox Sent DFT with 26, confirming with that DFT can be processed. 5/28 AbbaDox in attempt to clean up file. AbbaDox is removing all exams that do not end -26. MANA review GLV to see if there are other exams that need to be added. | When an exam code is scheduled in one of the Karas and Patt Walker locations, and "Dummy" diagnosis is added to the appointment, AbbaDox send Modified 26 in the outbound DFT interface
DFT Procedure and Location Modifer Mapping | If procedure matches identifier, and location matches Link to Category , link identifier will be sent as modifier in FT1.26 |  |  | 6/25 Completed adding locations Ozarks and Highlands to this generic list 6/18 Instances have been rearranged to match the description 6/8 Need to rearrange the values.in the Generic 6/1 Actions: There's a need to consider and Highlands and Ozardks also in this logic. 6/8 DS-1468 Ticket has been created to add location Highland locations and Ozark. | If exam code is scheduled, and appointment is scheduled at in Karas or PW location, AbbaDox will send modifier of RT and LT ; https://pinkypixels.atlassian.net/browse/DS-1468 | There's a need to consider and Highlands and Ozardks
DFT Procedure Modifer Mapping | If procedure matches identifier, link identifier will be sent as modifier in FT1.26 | AB5083 | Pass | 6/25 In ticket IN-3707, Brad's has requested a sample DFT that includes modifier from list and exam code. May require assistance from Britnney. 6/8 IN-3707 Tickets have been created to update all of the Exam codes in this list and to update OB DFT to include modifiers detailed on the Exam Code. Also accounted for the exam codes that Brittney added to file DFT_Exam_ Mapping file to account for additional exams that just have 26 modifier. 6/1 It's been decided that this list can be moved to Locl Procedures - Modifier section. Export list map modifier in list local procedure. 5/11 4. AbbaDox Sent DFT with 26^RT, confirming with that DFT can be processed. 5/11 5. Tried with an exam that does not end in -26 to determine if there's an issue with compendium in eCW | If exam code is scheduled, send the modifier of 26^LT, 26^RT, RT, or LT accordingly.
Add Diagnosis for Exam | If exam scheduled, add diagnosis to visit.