MANA / AbbaDox

| Meeting Date: | Wednesday, February 18, 2026 | Meeting Time | 10:00 AM EST |
| --- | --- | --- | --- |
| Location: | Teams Meeting |  |  |
| Facilitator | Join the meeting now Meeting ID: 281 654 499 189 Passcode: Hs2Ho7tm |  |  |

SharePoint Link: MANA – AbbaDox Careflow RIS SharePoint
Account Setup Workbook: MANA Account Setup Workbook

|  | Attendee | Party |
| --- | --- | --- |
| ☒ | Carrie Johnson | MANA |
| ☒ | Darron Mitchell | MANA |
| ☒ | Daniel Lad | MANA |
| ☒ | Dawn | MANA |
| ☒ | Ruben Gonzalez | AbbaDox |
| ☐ | Andreina Boudle | AbbaDox |
| ☐ | Rafael De Leon | AbbaDox |

- 7+ Locations, 120,000 Annual Studies

Meeting Minute

- Go Live Date Tentative – TBD - 2/11 Pending feedback on Hollogic and Onco. - UAT - IC - 2/11Billing workflow with ISC, AbbaDox - Completed - 1/28 Include MANA into this request RT-789 - BC - 1/28 Carrie to confirm with Kim sign-off on Billing Workflow, MANA – In Progress - 2/4 Team agreed to discontinue Monday and Tuesday meetings to completion workflow and app build. - Training - 2/12 Collateral for training one-to-one - Interfaces Feature-707 - Merge PACS. Scope: Uni. ORM,ADT,ORU 100% - MagView. Scope: Bid. ORM,ADT/ORU Tuesdays at 12.00 PM EST 90% - 1/21 Recent issues: - Addendum follow up required, AbbaDox – New - Action: Filter required for ADT, only send ADT when appointment is scheduled in breast center location, AbbaDox – Completed - 2/11 Interface testing with all procedures, MANA – In Progress - PowerScribe. Scope: Bid. ORM,ADT/ORU - Thursday at 12.00 PM EST 100% - 2/4 Action: Foreign Films: Update OB logic to trigger ORM upon NEW appointment status, AbbaDox – In Progress - 2/4 Follow up on linked studies from PT/CT. Issue: AbbaDox is displaying one of the two modalities in the report, not both. Accessions are AB2440 and AB2434, AbbaDox – completed - 2/4 Followed up with PS360 regarding this issue, update can be done by PS, PS – In Progress - 2/4 Custom field follow up to PowerScribe, PS – New - eCW. Scope: Bid. ORU,ADT,DFT,SIU/ORM, ADT (Steven Dominguez) Thursday at 2.00 PM EST 40% - 1/21 Mapping of Location/Rooms required - 2/4 Mapping file reviewed, MANA team will assist on mapping and will share document with Steven, MANA - Completed - 1/21 AbbaDox compendium to eCW must refined to only the procedures that will ever be submitted from eCW. Current compendium also has procedures required for migration, AbbaDox – Completed - 2/11 The last compendium provided is still good for eCW, AbbaDox has not created more procedures relevant to eCW, to be done closer to go live, AbbaDox - New - 2/4 Action: Request to not send OB SIU when order is created under a foreign film location, AbbaDox – In Progress - 2/4 Action: AbbaDox to account for Referring Practice NPI in OBR in ORU, AbbaDox – In Progress - Outreads Flatiron/OncoEMR HOG 5% - 2/4 Flat iron has requested resource assignment from OncoEMR, Once – Completed - 2/11 Kick-off required, Onco - New - Hollogic - 2/4 Ticket submitted to Hollogic, scope being defined by Hollogic, Hollogic – In Progress - Data Migration DS-696 - 2/11 MANA assisting on Merging patients, MANA – In Progress - 2/11 Report migration, AbbaDox – In Progress Account Configurations - 1/28 IC will adopt propose workflow of Foreign films via scheduling wizard - 2/4 AbbaDox to update rooms, procedures and build rules to accomodate HOG and general scheduling rules, AbbaDox - In Progress - MANA - IC Rules updates.xlsx - 1/28 Bug tickets reported by BC are being prioritized this week. - Combo Code Bug - Change of Complex Procedure Bug - 2/11 Tickets revised with MANA and sent back to dev. - 2/4 Request to use “New” Status when appointment is Rescheduled, AbbaDox - New - Enhancement: - 11/26 Recurrent Block Slots - 12/1 Request to not have all locations selected when scheduling by default, AbbaDox – New - Document Management - Reforma (Print) – No need Reforma Barcode - IC 1/21 Action: New forms available for upload, AbbaDox - Completed