MANA / AbbaDox

| Meeting Date: | Wednesday, August 27, 2025 | Meeting Time | 10:00 AM EST |
| --- | --- | --- | --- |
| Location: | Teams Meeting |  |  |
| Facilitator | Join the meeting now Meeting ID: 281 654 499 189 Passcode: Hs2Ho7tm |  |  |

SharePoint Link: MANA – AbbaDox Careflow RIS SharePoint
Account Setup Workbook: MANA Account Setup Workbook

|  | Attendee | Party |
| --- | --- | --- |
| ☒ | Carrie Johnson | MANA |
| ☒ | Darron Mitchell | MANA |
| ☒ | Daniel Lad | MANA |
| ☒ | Dawn | MANA |
| ☒ | Ruben Gonzalez | AbbaDox |
| ☐ | Andreina Boudle | AbbaDox |
| ☐ | Rafael De Leon | AbbaDox |

- 7+ Locations, 120,000 Annual Studies

Meeting Minutes

- Account Setup Workbook - 7/16 Phase 2 Review - Procedures will be divided into Imaging Breast and breast center, lists will be consolidated before upload, MANA – In Progress - 8/20 Imaging Center Procedures, MANA – Completed - 8/27 Procedure are ready for upload, AbbaDox - New - Referrings – In Progress - 8/13 If the referring provider is not a MANA referring provider, AbbaDox should send Facility NPI via HL7, AbbaDox – New (use OBR.16) - 8/27 Referring are ready for upload, AbbaDox - New - 7/16 Phase 3 Review - Rads: - 7/30 Determine if signature image is required, MANA – Completed - Electronic signature timestamp is enough. - SSO - 8/20 AbbaDox to setup call with IT and Ben, AbbaDox – Completed - 8/27 Meeting on 8/29 - Roles - 8/20 Role definition call required, AbbaDox – In Progress - 8/27 Role assignment and creation reviewed with Carrie. - 8/27 Call scheduled for 8/29 at 2.00 PM EST - Workflow Reviews - Intro to Settings 8/4 – 9.00 AM – #1 Completed - Intro to Settings 8/6 – 12.00 PM – #2 Completed - Onder Intake – 8/14 IC and 8/15 BC. - IC Order Intake - Completed - BH Order Intake – Completed - 8/20 Need to define utility for Faxio. - Pending Workflow - 8/14 IC Pending Workflow – Completed - 8/20 BC Pending Workflow – New - 8/20 Share additional times to reschedule review – Meeting on 8/27 - Scheduling - IC 8/27 Rescheduled to 2.00 PM EST - Note: 8/27 Determine if location can be filtered per user at scheduling Wizard, AbbaDox - New - Pre-registration - Registration - Technologist - Interfaces Feature-707 - 7/23 VPN Request Form required, MANA – Completed - Merge PACS. Scope: Uni. ORM,ADT,ORU - 8/27 Kick-off scheduled 8/29, AbbaDox ready to begin sending and receiving messages. - MagView. Scope: Bid. ORM,ADT/ORU - 7/16 Resource assigment required, Mana – New - 8/20 Pending on response from MV. - 8/27 AbbaDox to reply to kickoff meeting availability. - 8/13 AbbaDox setting up VPN, PSK has been sent, AbbaDox – In Progress - 7/30 OB ORM Interface logic should include Referrings NPI – This note has been added to the ticket. - 8/6 Note: MANA utilizes Dragon and PowerScribe to dictate. Nurses dictate from Dragon (Magview) so do not have an NPI. The client will be providing the NPI and Dictator ID in ASW. Interface logic needs to configured to map to Dictator ID if NPI is missing. - PowerScribe. Scope: Bid. ORM,ADT/ORU - 7/16 Resource assigment required, Mana – In Progress - 8/20 Pending on response from PW. - 8/7 SOW sent to Ben for Review, Mana – In Progress - 8/27 MANA has reached out Nuance, pending on response. - eCW. Scope: Bid. ORU,ADT,DFT,SIU/ADT (Steven Dominguez) - 7/16 Resource assigment required, Mana - New - 7/23 Note : OB ORU Interface should “hold” messages for 7 days for specific Referring NPIs. - 7/30 OB ORM Interface logic should include Referrings NPI - 8/6 OB ORU must include Facility NPI, Facility NPI is referenced in Reading physicians External ID. - 8/13 eCW cloud hosted, AbbaDox to determine if VPN is required, AbbaDox – In progress - Consider Ports to eCW Test environment prior to golive. - Outreads - 8/7 After further conversation, it’s been determined that AbbaDox needs to build a OB ORU to OncoEMR, SOW being sent to Onco, AbbaDox – Completed - 8/27 AbbaDox pending on SOW from MANA, Ben reached out to Jessica at HOG determine next steps MANA – In Progress - Data Migration DS-696 - 7/9 Merge .CSV Data upload template. Pt records with payers, historical exams, future exams, historical ORU. - 8/6 Create SFTP and share with Merge, AbbaDox – In Progress - Document Management - 7/23 Start thinking about document management in AbbaDox, MANA - New - eForm - 7/9 Access to JotForms - 7/23 Currently Merge only prints the router document, therefore AbbaDox could build this form electronically. There’s the potential of AbbaDox owning more of the documents for Imaging and breast center because the eForms can be sent downstream via HL7. - Reforma (Print) - 7/9 Upload forms to SharePoint, MANA - New - Radiology Report Templates - 7/23 Folders have been created in SharePoint to load templates per Imaging and breast center accordingly, MANA – In Progress - 7/30 Imaging center done, pending on Breast Center. - 8/13 Need to confirm on Breast Center, it appears available in SharePoint. - Complete - 8/20 Report Templates Upload – Abbadox - Completed - ScanDox