MANA / AbbaDox

| Meeting Date: | Wednesday, October 1, 2025 | Meeting Time | 10:00 AM EST |
| --- | --- | --- | --- |
| Location: | Teams Meeting |  |  |
| Facilitator | Join the meeting now Meeting ID: 281 654 499 189 Passcode: Hs2Ho7tm |  |  |

SharePoint Link: MANA – AbbaDox Careflow RIS SharePoint
Account Setup Workbook: MANA Account Setup Workbook

|  | Attendee | Party |
| --- | --- | --- |
| ☒ | Carrie Johnson | MANA |
| ☒ | Darron Mitchell | MANA |
| ☒ | Daniel Lad | MANA |
| ☒ | Dawn | MANA |
| ☒ | Ruben Gonzalez | AbbaDox |
| ☐ | Andreina Boudle | AbbaDox |
| ☐ | Rafael De Leon | AbbaDox |

- 7+ Locations, 120,000 Annual Studies

Meeting Minute

- Workflow Reviews - Technologist - IC 9/25 – Completed - BC 9/11 – Completed - BC Review with techs 10/10 - Billing - IC 10/02 Review – In Progress - Lung Follow Up Workflow - IC 10/09 Review – New - A-Z Workflow Recap - IC 11/16 – New - BC 10/29 – In Progress - Interfaces Feature-707 - 9/3 VPN: Same VPN will be used for Merge, MagView, PW and OnceEMR - Completed - Merge PACS. Scope: Uni. ORM,ADT,ORU - 10/1 Scheduling weekly meeting cadence – in progress - MagView. Scope: Bid. ORM,ADT/ORU - 10/1 Kickoff meeting on 10/7. - PowerScribe. Scope: Bid. ORM,ADT/ORU - 10/1 Project kick-off completed, pending on resource assignment. - eCW. Scope: Bid. ORU,ADT,DFT,SIU/ADT (Steven Dominguez) - 9/24 Pending on PM assignment, eCW - In Progress - 10/1 PM assigned pending on meeting availability, AbbaDox - New - Outreads Flatiron/OncoEMR HOG - 10/1 Pending on PM assignment, Flatiron- In Progress. ETA 10/15 - Data Migration DS-696 - Scope: Merge .CSV Data upload template. Pt records with payers, historical exams, future exams, historical ORU. - 9/11 AbbaDox pending on samples from Merge, AbbaDox - New - Account Configurations - Combo Codes - IC 10/1 - Completed - BC 10/1 - Completed - Questionnaires - IC 9/18 Review, IC – In Progress - BC 10/1 Amanda Revisiting Questionnaires – In Progress - Resource Scheduling Rules - IC 9/18 Review – New - BC 9/3, 9/15, 9/29 Review – In Progress - Notification Slots - IC – New - BC 9/29 Review – Completed - Complex Scheduling Rules - IC 9/18 Review – New - BC 9/29 Review – Completed - Reforma - IC 9/18 Review – In Progress - BC 9/19 Review – In Progress - Document Management - Reforma (Print) - IC 9/18 Upload registration documents to Reforma folder in Sharepoint. - 10/1 Documents available in Sharepoint, AbbaDox - New - BC 10/1 will pursue Reforma to print Router, Recommendation, and Risk Assessment - 10/1 Documents available in Sharepoint, AbbaDox – New - Edit Report Functionality - 10/1 Functionality needs to enable, AbbaDox - New - ScanDox (ScanDox not required .)