MANA / AbbaDox

| Meeting Date: | Wednesday, November 26, 2025 | Meeting Time | 10:00 AM EST |
| --- | --- | --- | --- |
| Location: | Teams Meeting |  |  |
| Facilitator | Join the meeting now Meeting ID: 281 654 499 189 Passcode: Hs2Ho7tm |  |  |

SharePoint Link: MANA – AbbaDox Careflow RIS SharePoint
Account Setup Workbook: MANA Account Setup Workbook

|  | Attendee | Party |
| --- | --- | --- |
| ☒ | Carrie Johnson | MANA |
| ☒ | Darron Mitchell | MANA |
| ☒ | Daniel Lad | MANA |
| ☒ | Dawn | MANA |
| ☒ | Ruben Gonzalez | AbbaDox |
| ☐ | Andreina Boudle | AbbaDox |
| ☐ | Rafael De Leon | AbbaDox |

- 7+ Locations, 120,000 Annual Studies

Meeting Minute

- Go Live Date Tentative - 2/17 - On-site assessment - 11/12 Request to meet on-site: January 6th. - Workflow Reviews - A-Z Workflow Recap - IC – In Progress - 11/26 Technologist workflow review recap required. - 11/5 Action: Ticket request being written, AbbaDox – In Progress - BC 10/29 – shifted towards configuration Q&A - Interfaces Feature-707 - Merge PACS. Scope: Uni. ORM,ADT,ORU Thursdays at 3.00 PM EST. 85% - 11/26 AbbaDox to send OB ORU. - MagView. Scope: Bid. ORM,ADT/ORU Tuesdays at 12.00 PM EST 90% - 11/26 AbbaDox received ORU. - Successfully received report: Amanda Zztest (AB1018) - PowerScribe. Scope: Bid. ORM,ADT/ORU - Thursday at 12.00 PM EST 90% - 11/26 Received report and Addendum on: Andreina Zztest123 (AB1003) - eCW. Scope: Bid. ORU,ADT,DFT,SIU/ADT (Steven Dominguez) Thursday at 2.00 PM EST 25% - 11/26 AbbaDox ready to receive samples to all the message types to - 172.16.25.11 : 6030. - Outreads Flatiron/OncoEMR HOG 5% - 11/12 AbbaDox to return signed BAA from HOG/OncoEMR - Data Migration DS-696 - Scope: Merge .CSV Data upload template. Pt records with payers, historical exams, future exams, historical ORU. - 11/14 - IC – Will need to create Merge Procedures in AbbaDox and also map other procedures. - BC – Local procedures in AbbaDox and Merge are one to one, so there’s will not be mapping needed. - 11/26 AbbaDox received file from Merge, it is now ready to upload samples, AbbaDox – In Progress - Account Configurations ETA: 12/5. - Complex Procedures - 11/12 BC – Secondary procedure should be treated as 0 minutes. - 11/26 Workaround determined via Combos codes. - Block FAB Feature-725 - 11/26 Ticket is on-going. - 12/1 Inquiry: In wizard, request to not have all locations selected when scheduling by default, AbbaDox - New - Document Management - Reforma (Print) - IC 9/18 Upload registration documents to Reforma folder in Sharepoint. - 11/26 Documents have been loaded, packages being built. - 12/1 Lynette will provide additional forms to load. - BC 10/1 will pursue Reforma to print Router, Recommendation, and Risk Assessment - 11/26 Documents have been loaded, packages being built, AbbaDox - New